## Transportation Readiness
Each Category Below will have a detailed Workplan | Task | Start Date | End Date | Task Owner | Status | Comments
Not started, Complete, In process
LICENSURE, ACCREDITATION, CERTIFICATION Lead: Mario | Office location identified | 2018-09-01 | 2018-11-01
| Licensed business in RI | 2018-09-01 | 2018-11-01
| Register as State vendor | 2018-09-01 | 2018-11-01
| PUC licensure ? | N/A | 2018-11-01
TRANSPORTATION PROGRAM ADMINISTRATION Lead: Jason/Mario | Key management staff in RI | 2018-08-09 | 2018-11-01
| Weekly Status Meetings | 2018-08-09 | 2018-12-31
| RI Works consideration | 2018-09-01 | Ongoing
| Unemployment etc | 2018-09-01 | 2018-11-01
| Encourage M/WBE | 2018-09-01 | Ongoing
| Policy and Procedural Manual | 2018-09-01 | 2018-11-01
| Implementation Plan | Auth to Proceed (see below) | 2018-09-01
| Websites, Mobile Applications & Other Innovations | 2018-09-01 | 2018-10-01
TRANSPORTATION PROGRAM ELIGIBILITY AND PROGRAM ENROLLMENT Lead: NEED | Medicaid Eligible and Enrolled Recipients | TBD | 2018-11-01
| Temporary Assistance for Needy Families (TANF) | TBD | 2018-11-01
| Non-Medicaid Elderly Population | TBD | 2018-11-01
| Process Denial of Service Determinations | TBD | 2018-11-01
RECIPIENT ENROLLMENT AND DISENROLLMENT Lead: NEED | Elderly Transportation Program | 2018-09-01 | 2018-11-01
| Eligibility Procedures | 2018-09-01 | 2018-11-01
| Eligibility Verification | 2018-09-01 | 2018-11-01
| Receive eligibility file from EOHHS | 2018-09-01 | 2018-11-01
| Challenging member behavior policy and procedure | 2018-09-01 | 2018-12-01
| Attendant (escort) policy | 2018-09-01 | 2018-12-01
| Stakeholder education | 2018-09-01 | 2018-11-01
| Disenrollment policy and procedure | 2018-09-01 | 2018-11-01
LEVELS OF SERVICE AND MODES OF TRAVEL Lead: Mario | Curb-to-Curb Service | 2018-09-01 | 2018-11-01
| Door to Door Service | 2018-09-01 | 2018-11-01
| Services available 24/7, 365 days a year. | 2018-09-01 | 2018-12-01
| Public Transit (bus) | 2018-09-01 | 2018-11-01
| Limited public vehicle (sedan) | 2018-09-01 | 2018-11-01
| Ride-Share Program (Uber/Lyft) | 2018-09-01 | 2018-11-01
| Public Motor Vehicle | 2018-09-01 | 2018-11-01
| Multi-Passenger Van | 2018-09-01 | 2018-11-01
| Wheelchair Van | 2018-09-01 | 2018-11-01
| Ambulance (stretcher van, ALS/BLS) | 2018-09-01 | 2018-11-01
| Mileage Reimbursement | 2018-09-01 | 2018-11-01
COORDINATION OTHER HEALTH/ SOCIAL SERVICES AVAILABLE TO RECIPIENTS Lead: Jason/Mario | Managed Care Organizations | Auth to Proceed | 12/1/18
| Accountable Entities | Auth to Proceed | 2018-12-01
| RI Public Transit Authority | Auth to Proceed | 2018-12-01
TRANSPORTATION PROVIDER NETWORKS Lead: Jason/Mario | TP supply adequacy | Auth to Proceed | 2018-11-01
| TPs insured | Auth to Proceed | 2018-11-01
| TPs licensed, certified, permitted | Auth to Proceed | 2018-11-01
| TP selection criteria | Auth to Proceed | 2018-11-01
| Contingency plans for unexpected peak transportation demands | 2018-09-01 | 2018-11-01
| Recovery policy | 2018-09-01 | 2018-11-01
| Incentive program policy and procedure if applicable | 2018-09-01 | 2018-11-01
| Fraud Waste and Abuse policy | 2018-09-01 | 2018-12-01
| Authorizing services | Auth to Proceed | 2018-10-01
| Scheduling services | Auth to Proceed | 2018-10-01
| Managing payments | Auth to Proceed | 2018-10-01
| Making payments | Auth to Proceed | 2018-10-01
| TP contracts | Auth to Proceed | 2018-11-01
| TP contracts executed | Auth to Proceed | 2018-11-01
| TP monitoring policy and procedures | 2018-09-01 | 2018-12-01
| Corrective action process | 2018-09-01 | 2018-12-01
| TP termination process | 2018-09-01 | 2018-12-01
| Alternative transportation options | 2018-09-01 | 2018-11-01
| Post-trip Review and Verification | 2018-09-01 | 2018-11-01
| Pre trip Review and Trip verification | 2018-09-01 | 2018-11-01
| Training events and training materials | 2018-09-01 | 2018-11-01
| Process Retroactive Eligibility Claims | 2018-09-01 | 2018-11-01
TRANSPORTATION PROVIDER AND VEHICLE REQUIREMENTS Lead: Jason/Mario | Vehicle compliance policy | 2018-09-01 | 2018-11-01
| AVL capacity | 2018-09-01 | 2018-11-01
| ADA compliance | 2018-09-01 | 2018-12-01
| Permits and licenses | Auth to Proceed | 2018-11-01
| TPs located in RI | Auth to Proceed | Ongoing
| Background checks | Auth to Proceed | Ongoing
| TP training curriculum: CPR, HIPAA, Cult Comp, Def Driver | 2018-09-01 | 2018-11-01
| TP identification | Auth to Proceed | 2018-12-01
BUSINESS OFFICE AND CALL CENTER LOCATION Lead: Jason/Mario | Co-located in RI | 2018-08-09 | 2018-10-01
| Staff training curriculum | 2018-09-01 | 2018-11-01
| Fully staffed | Auth to Proceed | 2018-11-01
| Fully equipped | Auth to Proceed | 2018-11-01
RHP Notices
TRANSPORTATION RECIPIENT SERVICES Lead: Jason/Mario | Member materials | 2018-09-01 | 2018-11-01
| Toll free number(s) | Auth to Proceed | 2018-12-01
| 24/7 operations | Auth to Proceed | 2019-01-01
| Call flow routing | Auth to Proceed | 2018-12-01
| Telephone Device for the Deaf (TDD) | Auth to Proceed | 2018-12-01
| Automatic Call Distributor (ACD) | Auth to Proceed | 2018-12-01
| Call Tracking | Auth to Proceed | 2018-12-01
| Response standards for member service | 2018-09-01 | 2018-12-01
| Telephone system back up system | Auth to Proceed | 2018-12-01
| Determine the Mode of Transport | Auth to Proceed
| Call Extraction and Reporting | Auth to Proceed
TRANSPORTATION PROVIDER SERVICES Lead: Jason/Mario | Toll free line for provider relations | Auth to Proceed | 2018-12-01
| Personnel policy | 2018-09-01 | 2018-12-01
| Response standards for Provider service | 2018-09-01 | 2018-12-01
| Claims Processing Function | Auth to Proceed | 2018-10-01
| Prior Authorization | Auth to Proceed | 2018-10-01
| Provider complaint policy | 2018-09-01 | 2018-11-01
| Provider Manual | 2018-09-01 | 2018-11-01
| Process Trip Assignments | Auth to Proceed | 2018-11-01
PAYMENTS Lead: Need | Ability to receive 834 enrollment report | Auth to Proceed | 2018-11-01
| Receive capitation payments | Auth to Proceed | 2018-11-01
|  | Auth to Proceed | 2018-11-01
| Receive ETP and TANF payments | Auth to Proceed | 2018-11-01
| Fee for service payment receipt | Auth to Proceed | 2018-11-01
| Claims Processing and MIS | Auth to Proceed | 2018-11-01
| Audit capacity | Auth to Proceed | 2018-11-01
| Financial Data Reporting | Auth to Proceed | 2018-11-01
| Rate Certification | 2018-08-09 | 2018-09-15
GUARANTEES, WARRANTIES, AND CERTIFICATIONS Lead: Mario | Broker Certification of Truthfulness | 2018-08-09 | 2018-12-01
| Broker Certification of Legality | 2018-08-09 | 2018-12-01
| Performance Bond or Substitutes | 2018-08-09 | 2018-08-16
| Subcontracts | 2018-08-09 | 2018-12-01
| Professional liability insurance | 2018-08-09 | 2018-08-16
| Workers' compensation | 2018-08-09 | 2018-08-16
| Comprehensive liability insurance | 2018-08-09 | 2018-12-01
| Property damage insurance | 2018-08-09 | 2018-12-01
| Errors and Omissions insurance | 2018-08-09 | 2018-12-01
| Automobile Liability | 2018-08-09 | 2018-08-16
PERSONNEL Lead: Jason/Mario | Personnel policy and procedures | 2018-09-01 | 2018-11-01
| Full staff compliment | 2018-08-09 | 2018-11-01
| Staff fully trained | Auth to Proceed | 2018-12-01
RECORDS RETENTION Lead: Jason/Mario | Ability to maintain for 10 years | 2018-09-01 | Ongoing
| Service delivery | 2018-09-01 | Ongoing
| Financial statements | 2018-09-01 | Ongoing
PERFORMANCE STANDARDS AND DAMAGES Lead: Jason/Mario | Electronic report submission | 2018-08-09 | 2018-11-01
| 837 submission | 2018-08-09 | 2018-11-01
| 277CA reports | 2018-08-09 | 2018-11-01
| Encounter data and reporting | Auth to Proceed | 2018-11-01
| Grievance and Appeals data and reporting | Auth to Proceed | 2018-11-01
| Quality Assurance data and reporting | Auth to Proceed | 2018-11-01
| Quality Improvement & Operations Plan | Auth to Proceed | 2018-11-01
| Recipient Satisfaction Data and reporting | Auth to Proceed | 2018-11-01
| Fraud And Abuse reports | Auth to Proceed | 2018-11-01
| Recovery reporting | Auth to Proceed | 2018-11-01
| Utilization Review policy | 2018-09-01 | 2018-12-01
| Performance reports | Auth to Proceed | 2018-12-01
| Liquidated Damages | 2018-08-09 | 2018-11-01
| Quality Assurance policy | 2018-09-01 | 2018-12-01
| Complaint data and reporting | Auth to Proceed | 2018-12-01
COMPLIANCE Lead: Jason/Mario | Disclosure of Ownership and Control Interest | 2018-09-01 | 2018-12-01
COMPLAINTS, GRIEVANCE AND APPEALS Lead: Jason/Mario | Complaint Resolution policy | 2018-09-01 | 2018-11-01
| Grievance Process policy | 2018-09-01 | 2018-11-01
| Expedited Resolution of Appeals process | 2018-09-01 | 2018-11-01
ANNUAL COMPLIANCE AUDIT Lead: Jason/Mario | Audit compliance per contract | 2018-09-01 | 2018-11-01
INSPECTION OF WORK PERFORMED Lead: Jason/Mario | Marketing materials | 2018-09-01 | 2018-11-01
| Written materials | 2018-09-01 | 2018-11-01
| Recipient Communication | 2018-09-01 | 2018-11-01
| Partner/Stakeholder Communication/Engagement | Auth to Proceed | 2018-11-01
| Multilingual capacity | 2018-10-01 | 2018-11-01
| Maintain Confidential Information | 2018-10-01 | 2018-11-01
| T/P subcontracts | Auth to Proceed | 2018-11-01
OTHER CONTRACT TERMS AND CONDITIONS Lead: Jason/Mario | Conflict of Interest | Auth to Proceed | 2018-12-01
| Reporting of Political Contributions | Auth to Proceed | 2018-12-01
| Environmental Tobacco Smoke | Auth to Proceed | 2018-12-01
| Other workplace federal requirements | Auth to Proceed | 2018-12-01
Auth to Proceed = | Activity to begin upon EOHHS' receipt of an Authorization to Proceed letter from Purchases to allow bidder to proceed with certain tasks prior to issue of Purchase Order.