## Transportation Readiness
Each Category Below will have a detailed Workplan | Task | Start Date | End Date | Task Owner | Status | Comments
Not started, Complete, In process
LICENSURE, ACCREDITATION, CERTIFICATION Lead: Mario | Office location identified | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Licensed business in RI | 2018-09-01 | 2018-11-01 | Jason/Mario | Complete
| Register as State vendor | 2018-09-01 | 2018-11-01 | Jason/Mario | Complete
| PUC licensure ? | N/A | 2018-11-01 | Mario | Complete | Broker does not need license
TRANSPORTATION PROGRAM ADMINISTRATION Lead: Jason/Mario | Key management staff in RI | 2018-08-09 | 2018-11-01 | Jason/Mario/Lissa/Marlanea | In process
| Weekly Status Meetings | 2018-08-09 | 2018-12-31 | Jason/Mario/Lissa/Marlanea | In process
| RI Works consideration | 2018-09-26 | Ongoing | Jason/Mario | In process | Lissa to touch base with Kim Rauch
| Unemployment etc | 2018-09-26 | Ongoing | Jason/Mario | In process
| Encourage M/WBE | 2018-09-26 | Ongoing | Jason/Mario | In process | DOA oversight in play
| Policy and Procedural Manual | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Implementation Plan | 2018-09-26 | 2018-09-01 | Jason/Mario | In process
| Websites, Mobile Applications & Other Innovations | 2018-09-26 | Ongoing | Jason/Mario | In process
TRANSPORTATION PROGRAM ELIGIBILITY AND PROGRAM ENROLLMENT Lead: NEED | Medicaid Eligible and Enrolled Recipients | 2018-09-26 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| Temporary Assistance for Needy Families (TANF) | 2018-09-26 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process | Potential DHS removal of program from brokerage
| Non-Medicaid Elderly Population | 2018-09-26 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| Process Denial of Service Determinations | 2018-09-26 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
RECIPIENT ENROLLMENT AND DISENROLLMENT Lead: NEED | Elderly Transportation Program | 2018-09-26 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| Eligibility Procedures | 2018-09-26 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| Eligibility Verification | 2018-09-26 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| Receive 834 eligibility file from EOHHS | 2018-09-26 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| Challenging member behavior policy and procedure | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Attendant (escort) policy | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Stakeholder education/awareness plan | 2018-09-26 | Ongoing | Jason/Mario | In process
LEVELS OF SERVICE AND MODES OF TRAVEL Lead: Mario | Curb-to-Curb Service | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Door to Door Service | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Services available 24/7, 365 days a year. | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Public Transit (bus) | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Ride-Share Program (Uber/Lyft) | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Public Motor Vehicle | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Multi-Passenger Van | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Wheelchair Van | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Ambulance (stretcher van, ALS/BLS) | 2018-09-26 | 2018-11-01 | Jason/Mario | In process | Received policy
| Mileage Reimbursement | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
COORDINATION OTHER HEALTH/ SOCIAL SERVICES AVAILABLE TO RECIPIENTS Lead: Jason/Mario | Managed Care Organizations | 2018-09-26 | Ongoing | Jason/Mario | In process
| Accountable Entities | 2018-09-26 | Ongoing | Jason/Mario | In process
| RI Public Transit Authority | 2018-09-26 | Ongoing | Jason/Mario | In process
| High utilizing providers (Adult Day, OTP, Dialysis etc. | 2018-09-26 | Ongoing | Jason/Mario | In process
TRANSPORTATION PROVIDER NETWORK Lead: Jason/Mario | TP supply adequacy | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| TPs insured | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| TPs licensed, certified, permitted | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| TP selection criteria | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Contingency plans for unexpected peak transportation demands | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Recovery policy | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Incentive program policy and procedure if applicable | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Fraud Waste and Abuse policy | 2018-09-26 | 2018-12-01 | Jason/Mario & Program Integrity | In process
| Authorizing services | 2018-09-26 | 2018-10-01 | Jason/Mario | In process
| Scheduling services | 2018-09-26 | 2018-10-01 | Jason/Mario | In process
| Managing payments | 2018-09-26 | 2018-10-01 | Jason/Mario | In process
| Making payments | 2018-09-26 | 2018-10-01 | Jason/Mario | In process
| TP contracts | 2018-09-26 | 2018-11-01 | Jason/Mario & EOHHS Legal | Complete
| TP contracts executed | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| TP monitoring policy and procedures | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| TP Corrective action process | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| TP termination process | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Alternative transportation options | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Post-trip Review and Verification | 2018-09-26 | 2018-11-01 | Jason/Mario | In process | Received Incdient/Accident report
| Pre trip Review and Trip verification | 2018-09-26 | 2018-11-01 | Jason/Mario | Complete | Received Pre-Trip Inspection Report, Vehicle Inspection Report and Guidelines
| Training events and training materials | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Process Retroactive Eligibility Claims | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Vehicle compliance policy | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| AVL capacity | 2018-09-26 | 2018-11-01 | Jason/Mario | In process | EOHHS granted 90 day grace period from 1/1/19
| ADA compliance | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Permits and licenses | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| TPs located in RI | 2018-09-26 | Ongoing | Jason/Mario | In process
| Background checks | 2018-09-26 | Ongoing | Jason/Mario | In process
| TP training curriculum: CPR, HIPAA, Cult Comp, Def Driver | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| TP identification | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
BUSINESS OFFICE AND CALL CENTER LOCATION Lead: Jason/Mario | Co-located in RI | 2018-08-09 | 2018-10-01 | Jason/Mario | In process | Concern with call center reps working from home.
| Staff training curriculum | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Fully staffed | 2018-09-26 | 2018-11-01 | Jason/Mario | In process | Concern with management presence in RI
| Fully equipped | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Personnel Policy and Procedures | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
RHP Notices |  |  |  |  | Not started
Not started
Not started
Not started
Not started
Not started
TRANSPORTATION RECIPIENT SERVICES Lead: Jason/Mario | Member materials | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Toll free number(s) | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| 24/7 operations | 2018-09-26 | 2019-01-01 | Jason/Mario | In process
| Call flow routing | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Telephone Device for the Deaf (TDD) | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Multilingual capacity | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Automatic Call Distributor (ACD) | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Call Tracking | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Response standards for member service | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Telephone system back up system | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Determine the Mode of Transport | 2018-09-26 |  | Jason/Mario | In process
| Call Extraction and Reporting | 2018-09-26 |  | Jason/Mario | In process
TRANSPORTATION PROVIDER SERVICE DELIVERY Lead: Jason/Mario | Toll free line for provider relations | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Response standards for Provider service | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Claims Processing Function | 2018-09-26 | 2018-10-01 | Jason/Mario | In process
| Prior Authorization | 2018-09-26 | 2018-10-01 | Jason/Mario | In process
| Provider complaint policy | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Provider Manual | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Process Trip Assignments | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
PAYMENTS Lead: Need
| Receive capitation payments | 2018-09-26 | 2018-11-01 | NEMT Team/Fiscal & IT & Data | In process
|  | 2018-09-26 | 2018-11-01 | NEMT Team/Fiscal & IT & Data | In process
| Receive ETP and TANF payments | 2018-09-26 | 2018-11-01 | NEMT Team/Fiscal & IT & Data | In process
| Claims Processing and MIS | 2018-09-26 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| Audit capacity | 2018-09-26 | 2018-11-01 | NEMT Team/Fiscal | In process | Received Provider audit document
| Financial Data Reporting | 2018-09-26 | 2018-11-01 | NEMT Team/Fiscal & IT & Data | In process
| Rate Certification | 2018-08-09 | 2018-09-15 | NEMT Team/Fiscal | Complete | Not necessary
GUARANTEES, WARRANTIES, AND CERTIFICATIONS Lead: Mario | Broker Certification of Truthfulness | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Broker Certification of Legality | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Insurance endorsement | 2018-08-09 | 2018-12-01 | Jason/Mario | Complete
| Performance Bond or Substitutes | 2018-08-09 | 2018-08-16 | Purchases | Complete
| Professional liability insurance | 2018-08-09 | 2018-08-16 | Purchases | Complete
| Workers' compensation | 2018-08-09 | 2018-08-16 | Purchases | Complete
| Comprehensive liability insurance | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Property damage insurance | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Errors and Omissions insurance | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Automobile Liability | 2018-08-09 | 2018-08-16 | Purchases | Complete
RECORDS RETENTION Lead: Jason/Mario | Ability to maintain for 10 years | 2018-09-26 | Ongoing | Jason/Mario | In process
| Service delivery | 2018-09-26 | Ongoing | Jason/Mario | In process
| Financial statements | 2018-09-26 | Ongoing | Jason/Mario | In process
| Maintain Confidential Information | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
PERFORMANCE STANDARDS AND DAMAGES Lead: Jason/Mario | Electronic report submission | 2018-08-09 | 2018-11-01 | Jason/Mario | In process
| 837 submission | 2018-08-09 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| 277CA reports | 2018-08-09 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| Encounter data and reporting | 2018-09-26 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| Quality Assurance policy | 2018-09-26 | 2018-12-01 | Jason/Mario | Complete
| Quality Assurance data and reporting | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Quality Improvement & Operations Plan | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Recipient Satisfaction Data and reporting | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Fraud And Abuse reports | 2018-09-26 | 2018-11-01 | NEMT Team/Progrsm Integrity | In process
| Recovery reporting | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Utilization Review policy | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Performance reports | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
| Liquidated Damages | 2018-08-09 | 2018-11-01 | Jason/Mario | In process | EOHHS granted 180 grace period from start of contract.
COMPLIANCE Lead: Jason/Mario | Disclosure of Ownership and Control Interest | 2018-09-26 | 2018-12-01 | Jason/Mario | Complete
COMPLAINTS, GRIEVANCE AND APPEALS Lead: Jason/Mario | Complaint Resolution policy | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Grievance Process policy | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Expedited Resolution of Appeals process | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Grievance and Appeals data and reporting | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Complaint data and reporting | 2018-09-26 | 2018-12-01 | Jason/Mario | In process
ANNUAL COMPLIANCE AUDIT Lead: Jason/Mario | Audit compliance per contract | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
INSPECTION OF WORK PERFORMED (EOHHS APPROVAL) Lead: Jason/Mario | Marketing materials | 2018-09-26 | 2018-11-01 | Jason/Mario | In process | Received RI postcard and Website text
| Written materials | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Recipient Communication | 2018-09-26 | 2018-11-01 | Jason/Mario | In process
| Partner/Stakeholder/Facility Communication/Engagement | 2018-09-26 | 2018-11-01 | Jason/Mario | In process | Received Communication and Education Plan, Facility Intro Letter, MTM overview presentation and slides for MTM overview presentation
| Multilingual capacity | 2018-09-26 | 2018-11-01 | Jason/Mario | In process