Title:  Rhode Island/MTM Implementation Meeting

Date:  Thursday, November 15, 2018

Dial In: 1-408-792-6300 	Code:  809 400 491

MTM Attendees

Shane Oskins, Senior Manager, Contact Center

Melissa Workman, Manager Community Outreach & Training

Nic Simmons, Fleet Analyst, Logistics

Casey Mayo, Fleet Analyst, Logistics

Brian Arnold, Regional Director, Logistics – East

Tom Hoth, Regional Director, Logistics – Central

Zach Stern, Provider Management Representative

Ashley Wright, Marketing Manager

Justin Cannavan, Director, Business Technology Engagement

Kim Clark, Regional VP - East

Stacy Brune, Manager Business Implementation

Valerie Barr, Director, Business Implementation

Sherry Moore, Project Manager, Business Implementation

Dana Hofer, Trainer

Jessica Krueger, Supervisor, Training

EOHHS Attendees

Mario Olivieri

Marlanea Peabody

Lissa DiMauro

Jason Lyon

Diana

January Angeles

Kristen Sousa

Agenda Topics:

Project Milestones

  - Historical data: 10/10/2018

  - Recurring Trip data: 10/19/2018

  - Protocols Approved: 11/21/2018

  - Readiness Review: 11/21/2018

  - Phone go-live: 12/18/2018

  - Transportation Start: 1/1/2019

- RISKS - Kim

  - Historical Data/Discrepancies in Trip Volume/Mode– EOHHS

  - Recurring Trip Data

    - Facility Introduction letter

  - ETP member data file

  - Toll Free Number Paperwork (ResPorg) - EOHHS

    - LC Carrier

    - LC Carrier Contact information

    - LC Carrier bill with toll free number included

    - LC temporary phone line created

- Logistics Management – Zach Stern

  - Transportation Provider Recruitment & Contracting

    - Fleet build

    - Contracts

    - Credentialing

    - RIPTA

- Protocols – EOHHS

- Staffing Update – Melissa

  - Program Director – Hired, start date 11/19/2018.

  - Support Staff

- TP Manager – Hired, start date 11/19/2018.

- Provider Management Rep - Hired, start date 11/19/2018.

- CC Manager - Hired, start date 11/19/2018.

- CC Supervisor - Hired, start date 11/19/2018.

- Recipient Advocate – EOHHS approval of request.

- Communication Plan – Dana/Justin B

  - External Stakeholder Communication

    - Facility Outreach

    - Transportation Provider Training w/o 11/5/2018

      - Virtual town hall on 11/5/2018

      - 4 live training town halls in December 12.3; 12.5; 12.7; 12.8

        - Training materials used in these sessions – MTM

  - Supporting Documentation for approval – included new versions on MTM SFTP site via EOHHS readiness checklist

    - State Resource Guide

    - Town Hall Sign in Sheet

    - Communication and Education Plan – RI

    - Facility Implementation Spreadsheet

    - Facility Intro Letter

    - MTM Overview Presentation

- Deliverable Approval

  - Deliverable Template (large file share)

    - Updated document saved as 11.12.2018

    - Question on COI’s & Broker Certification of Truthfulness

  - Ambulance Transportation Provider Contracts

    - Ambulance Provider Handbook - RI 2019

  - Vehicle Inspection Plan & Supporting Documents

    - MTM Provider Audit – RI 2019 – MTM returned to EOHHS 11/14

    - RI Vehicle Inspection Form – MTM returned to EOHHS 11/14

  - Recipient Education Materials

    - Rhode Island Postcard Text

    - Rhode Island Website Text

  - Contact Center Materials

    - CC Urgent Request Guidelines

    - Standard distance verification form

    - Authorization for Transportation Request form

  - Transportation Provider Manual -– MTM returned to EOHHS 11/14

  - Transportation Provider Training Materials – included in MTM SFTP via Readiness Checklist

  - Gas Mileage Reimbursement Materials

    - MTM Currency Welcome Letter

    - RI ACA Language Insert

    - Audit Recoupment Letter

  - Quality & Compliance Materials – 11/16/2018

    - Member Behavior – Warning Letter

    - Member Behavior – Action Taken Letter

    - Member Behavior – Education Letter

    - State Denial Letter – Rhode Island

    - Complaint Resolution Letter – Rhode Island

    - No show letter for level 2 members

    - No show letter for level 3 members

  - Reports

    - Monthly Client Summary Report (3.10.10.1.3)

    - Trip detail report (Sample PLAN_L_DETAIL_MONTH_YEAR) (3.10.10.1.3)

    - Contact Center Report (3.10.10.1.2)

      - Call Stats by Queue

      - Call Stats by Plan

      - EOHHS to determine if they need to have call stats broken out by plan (Medicaid, TANF, ETP) – DUE 11/9/2018

    - Claims Timeliness Report (Sample Plan Timeliness ) (3.10.6.2)

    - TP Monthly Report Card (3.10.10.1.1)

    - Monthly Complaint Report (3.10.10.1.4)

    - Sample FWA Report (3.7 Fraud, Waste and Abuse Reporting)

    - Accident Incident Client Report (3.10.1.7 Report Accidents, Injuries, and Incidents)

    - Sample Pre/Post Dashboard (3.10.3.2.1 Pre-trip Review and Verification)

    - Rhode Island Dashboard (3.10.10.1.3 Transportation Data Report)

| Action Item Log |  |  |  |  |
| --- | --- | --- | --- | --- |
| Task Number / Item |  | Owner | Status | Due Date |
| 1 | Encounter data | EOHHS | Request to DXC & EOHHS | 11/21/2018 |
| 2 | Standing Orders with Member names & addresses | EOHHS | With EOHHS legal | 11/6/2018 |
| 3 | Protocol Feedback | EOHHS | Complete | 11/9/2018 |
| 4 | Operational Day Treatment/Adult Day Care Requests | MTM | Complete | 11/9/2018 |
| 5 | Quality & Compliance Material Review/Approval | EOHHS | In Progress | 11/16/2018 |
| 6 | Member No Show Process | MTM | Complete – with notes | 11/8/2018 |
| 7 | Credentialing Questions | MTM | Complete – with notes | 11/8/2018 |
| 8 | MTM Report Samples Feedback/Approval | EOHHS | In Progress | 11/16/2018 |
| 9 | TP Logistics Meeting with Zach | EOHHS | Complete | 11/9/2018 |
| 10 | Deliverables Review/Approval | EOHHS | In Progress | 11/9/2018 |
| 11 | Bus Reimbursement Process | MTM/EOHHS | In Progress | 11/16/2018 |
| 12 |  |  |  |  |
| 13 |  |  |  |  |
| 14 |  |  |  |  |
| 15 |  |  |  |  |
| 16 |  |  |  |  |
| 17 |  |  |  |  |
| 18 |  |  |  |  |