Transportation Transition

Daily check in

11/28/18 - 8:30-9:00am

Virks 3rd Floor Room 302

Agenda

Yesterday’s Action Items:

TP Network adequacy

State Plan and Regs - Maria

DXC provider list – Marlanea, Jason, Steve

Reporting template review - Mark

Postcard Text - Jason

Finance/Fiscal - Mario

Site Visits - Jason

Adding Internal in-person meetings - Jason

Continuity of care confirmation – Jason

- Progress to date is on schedule

- Mark’s participation – Document review/reports

- Stakeholder meetings updates from Diana/Brenna

- TP network adequacy

- Line-by-line review of project plan for this week and beyond

- Questions/Concerns

This Week’s Meeting Schedule

Transition meetings:

  - Monday 11/26, 2-3 PM	MTM Webex – Eligibility and Encounter (room 331)

  - Tuesday 11/27, 3-4 PM	MTM Webex – Implementation (room 302)

  - Wednesday 11/28, 12-1 PM	MTM/RIPTA/EOHHS – Bus Passes (room 302)

  - Wednesday 11/28, 3-4 PM	LGTC/EOHHS Transition Call (Data transfer) (room 302)

  - Thursday 11/29, 2-3 PM	MTM Webex – Implementation (room 214)