

**Title: Rhode Island/MTM Implementation Meeting**

**Date**: Tuesday, December 4, 2018

**Dial In:** 1-408-792-6300 **Code:** 288 843 927

**MTM Attendees**

Shane Oskins, Senior Manager, Contact Center

Melissa Workman, Manager Community Outreach & Training

Nic Simmons, Fleet Analyst, Logistics

Casey Mayo, Fleet Analyst, Logistics

Brian Arnold, Regional Director, Logistics – East

Tom Hoth, Regional Director, Logistics – Central

Zach Stern, Provider Management Representative

Ashley Wright, Marketing Manager

Justin Cannavan, Director, Business Technology Engagement

Kim Clark, Regional VP - East

Stacy Brune, Manager Business Implementation

Valerie Barr, Director, Business Implementation

Sherry Moore, Project Manager, Business Implementation

Dana Hofer, Trainer

Jessica Krueger, Supervisor, Training

Michele Lucas, Chief Marketing Officer

**EOHHS Attendees**

Mario Olivieri

Marlanea Peabody

Jason Lyon

January Angeles

Kristen Sousa

Maria Narishkin

Steve

Meghan

**Agenda Topics:**

1. Member Communication
* Medicaid
* ETP
* TANF
1. Recurring Trips
	1. Park Avenue Senior Care
	2. South Kingston Adult day Care
2. Logistics Management – Zach Stern
	1. RIPTA
	2. RI TP Association
		1. Fleet Recruitment/# Contracts Executed
		2. Ambulatory
		3. Wheelchair
		4. Stretcher/Ambulance
	3. Challenge Areas - EOHHS
	4. TP listing and corresponding number of vehicles
	5. TP contract signature pages
	6. Geo Access Map for entire Network
3. Communication Plan – Dana/Justin B
	1. External Stakeholder Communication
		1. Facility Outreach
			1. Listing of Medical Providers/Agencies
				1. Adult Day Care facilities
				2. Dialysis facilities
	2. Consumer Advisory Committee

|  |
| --- |
| **Action Item Log** |
| **Task Number / Item** | **Owner** | **Status** | **Due Date** |
| 1 | Encounter data  | EOHHS | Complete | 11/21/2018 |
| 2 | Standing Orders with Member names & addresses | EOHHS | With EOHHS legal | 11/6/2018 |
| 3 | Protocol Feedback | EOHHS | Complete | 11/9/2018 |
| 4 | Operational Day Treatment/Adult Day Care Requests | MTM | Complete | 11/9/2018 |
| 5 | Quality & Compliance Material Review/Approval | EOHHS | In Progress | 11/16/2018 |
| 6 | Member No Show Process | MTM  | Complete – with notes  | 11/8/2018 |
| 7 | Credentialing Questions | MTM | Complete – with notes | 11/8/2018 |
| 8 | MTM Report Samples Feedback/Approval | EOHHS | In Progress | 11/16/2018 |
| 9 | TP Logistics Meeting with Zach | EOHHS | Complete | 11/9/2018 |
| 10 | Deliverables Review/Approval | EOHHS | In Progress | 11/16/2018 |
| 11 | Bus Reimbursement Process | MTM/EOHHS | Complete | 11/16/2018 |
| 12 |  |  |  |  |
| 13 |  |  |  |  |
| 14 |  |  |  |  |
| 15 |  |  |  |  |
| 16 |  |  |  |  |
| 17 |  |  |  |  |
| 18 |  |  |  |  |