

**Title: Rhode Island/MTM Implementation Meeting**

**Date**: Tuesday, December 4, 2018

**Dial In:** 1-408-792-6300 **Code:** 288 843 927

**MTM Attendees**

Shane Oskins, Senior Manager, Contact Center

Melissa Workman, Manager Community Outreach & Training

Nic Simmons, Fleet Analyst, Logistics

Casey Mayo, Fleet Analyst, Logistics

Brian Arnold, Regional Director, Logistics – East

Tom Hoth, Regional Director, Logistics – Central

Zach Stern, Provider Management Representative

Ashley Wright, Marketing Manager

Justin Cannavan, Director, Business Technology Engagement

Kim Clark, Regional VP - East

Stacy Brune, Manager Business Implementation

Valerie Barr, Director, Business Implementation

Sherry Moore, Project Manager, Business Implementation

Dana Hofer, Trainer

Jessica Krueger, Supervisor, Training

Michele Lucas, Chief Marketing Officer

**EOHHS Attendees**

Mario Olivieri

Marlanea Peabody

Jason Lyon

January Angeles

Kristen Sousa

Maria Narishkin

Steve

Meghan

**Agenda Topics:**

1. Member Communication

* Medicaid
* ETP
* TANF

1. Recurring Trips
   1. Park Avenue Senior Care
   2. South Kingston Adult day Care
2. Logistics Management – Zach Stern
   1. RIPTA
   2. RI TP Association
      1. Fleet Recruitment/# Contracts Executed
      2. Ambulatory
      3. Wheelchair
      4. Stretcher/Ambulance
   3. Challenge Areas - EOHHS
   4. TP listing and corresponding number of vehicles
   5. TP contract signature pages
   6. Geo Access Map for entire Network
3. Communication Plan – Dana/Justin B
   1. External Stakeholder Communication
      1. Facility Outreach
         1. Listing of Medical Providers/Agencies
            1. Adult Day Care facilities
            2. Dialysis facilities
   2. Consumer Advisory Committee

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Action Item Log** | | | | |
| **Task Number / Item** | | **Owner** | **Status** | **Due Date** |
| 1 | Encounter data | EOHHS | Complete | 11/21/2018 |
| 2 | Standing Orders with Member names & addresses | EOHHS | With EOHHS legal | 11/6/2018 |
| 3 | Protocol Feedback | EOHHS | Complete | 11/9/2018 |
| 4 | Operational Day Treatment/Adult Day Care Requests | MTM | Complete | 11/9/2018 |
| 5 | Quality & Compliance Material Review/Approval | EOHHS | In Progress | 11/16/2018 |
| 6 | Member No Show Process | MTM | Complete – with notes | 11/8/2018 |
| 7 | Credentialing Questions | MTM | Complete – with notes | 11/8/2018 |
| 8 | MTM Report Samples Feedback/Approval | EOHHS | In Progress | 11/16/2018 |
| 9 | TP Logistics Meeting with Zach | EOHHS | Complete | 11/9/2018 |
| 10 | Deliverables Review/Approval | EOHHS | In Progress | 11/16/2018 |
| 11 | Bus Reimbursement Process | MTM/EOHHS | Complete | 11/16/2018 |
| 12 |  |  |  |  |
| 13 |  |  |  |  |
| 14 |  |  |  |  |
| 15 |  |  |  |  |
| 16 |  |  |  |  |
| 17 |  |  |  |  |
| 18 |  |  |  |  |