## Document Review
Document Name | Date due to EOHHS | Date Provided by MTM | Date Reviewed By EOHHS | Reviewed By | Approved? | Date Sent back to MTM | Date Updated Document Received | Date Reviewed | Reviewed By | Approved ? | Notes
ACA Language Insert | 2018-11-01 |  |  | Jason | No | 2018-11-16 |  |  |  | Yes | Sent back with our template
Ambulance provider handbook |  | 2018-10-11 | 2018-10-26 | Mario and Jason | Yes
Audit Recoupment Letter |  |  |  | Jason and Mario | Yes
Authorization for transportation request form |  |  |  | Jason and Mario | Yes
Bus Letter |  | 2018-11-19 | 2018-11-19 | Meghan | No | 2018-11-19 | 2018-11-19 | 2018-11-20 | Meghan | Yes
CC urgent request guidelines |  |  |  | Jason and Mario | Yes
Complaint resolution letter |  |  | 2018-11-20 | Meghan | No | 2018-11-20
Compliance plan | 2018-11-01 |  |  | Jason and Mario | Yes | [5 empty] | Provided 2018 Compliance Plan
Daily pre-trip inspection report | 2018-11-01 |  |  | Jason and Mario | Yes
Disaster Recovery |  | 2018-11-19 | 2018-11-19 | Ave | Yes | [5 empty] | Sent in lieu of staffing plan
Distance verification form |  |  |  | Jason and Mario | Yes | 2018-11-20
Facility Implementation Spreadsheet |  |  |  | Jason and Mario | No |  | 2018-11-20 |  | Jason | Yes
Facility intro letter |  |  |  | Jason and Mario | No |  | 2018-11-20 |  | Jason | Yes
FWA Integrity Plan | 2018-11-21 |  |  | Tom Bouchard | Yes
Generic RFI |  |  |  | Jason and Mario | Yes
GMR Trip Log doc |  |  |  | Jason and Mario | Yes
Implementation | 2018-10-15 | 2018-09-01 |  | Jason and Mario | yes
Language Attestation | 2018-12-15 |  |  | Jason and Mario | Yes
Level of Need - Ambulance |  |  |  | Jason and Mario | Yes
Level of Need - Standard |  |  |  | Jason and Mario | Yes
Member behavior - action taken |  |  |  | Jason | No | 2018-11-16
Member behavior - education letter |  |  |  | Jason | No | 2018-11-16
Member behavior - warning letter |  |  |  | Jason | No | 2018-11-21
MTM Currency Welcome Letter - no public transit (GMR Letter) |  | 2018-11-19 | 2018-11-19 | Meghan | No | 2018-11-19 | 2018-11-19 | 2018-11-20 | Meghan | Yes
MTM Incoming call guide |  |  |  | Jason and Mario | Yes
MTM overview PP |  |  |  | Jason | No | 2018-11-16 | 2018-11-21 |  | Jason | Yes | Sent back to EOHHS again
MTM Protocols |  |  |  | Jason | Yes
MTM Provider Audit |  |  |  | Jason and Mario | Yes
No Show letter level 2 |  |  |  | Meghan/Jason | Yes
No show letter lever 3 |  |  |  | Meghan | No | 2018-11-20
Policy 2001 New hire orientation |  | 2018-11-20 |  | Ave | Yes
Policy 413 Management of No Shows |  | 2018-11-20 |  | Meghan
Policy 435 Compliance and ethics |  | 2018-11-20 |  | Ave | Yes
Policy 437 Compliance and ethics education training/outreach |  | 2018-11-20 |  | Meghan | Yes
Policy 702 Annual compliance training |  | 2018-11-20 |  | Ave | Yes | [5 empty] | Submitted with Contract
Policy 753 Documentation of ongoing training |  | 2018-11-20 |  | Ave | Yes
Policy 9902 Regulatory Compliance |  | 2018-11-20 |  | Ave | Yes
Postcard Text | 2018-11-01 |  |  | Meghan | No | 2018-11-21
Procedue 602.004 Pre and post validation |  | 2018-11-20 |  | Ave | Yes
Procedure 606.001 Claims web application-verification of claims |  | 2018-11-20 |  | Ave | Yes
Procedure 700.002 sanction check search process |  | 2018-11-20 |  | Meghan | Yes
Provider Handbook | 2018-11-21 |  |  | Meghan | Yes
Quality Assurance Program | 12/1/2018 |  |  | Jason and Mario | Yes
REPORT - Accident/incident client report |  | 2018-11-02
REPORT - Claims timeliness report |  | 2018-11-02
REPORT - Contact Center report - Call Queue |  | 2018-11-02
REPORT - Contact Center report - Call stats |  | 2018-11-02
REPORT - Monthly client summary report
REPORT - Monthly complaint report |  | 2018-11-02
REPORT - RI dashboard |  | 2018-11-02
REPORT - Sample Denial Detail Report |  | 2018-11-02
REPORT - Sample FWA report |  | 2018-11-02
REPORT - Sample Plan Detail Month Year |  | 2018-11-02
REPORT - Sample pre/post dashboard |  | 2018-11-02
REPORT - TP Monthly Report Card
REPORT - Trip detail report
RI Operating procedures manual | 2018-11-21 | 2018-11-20 | [8 empty] | See Ops Manual tab for checklist of P&Ps
Staffing plan | 2018-11-01 | 2018-09-25 |  | Contract review | Yes | [5 empty] | Submitted with Contract
State Denial Letter |  | 2018-11-09 |  | Meghan
State resource guide |  | 2018-11-20 |  | Jason | No | 2018-11-21
Town hall sign-in |  |  |  | Comm. Team
TP Appendix B | 2018-11-15 | 2018-11-12 |  | Jason and Mario | Yes
TP Helpdesk |  | 2018-11-12 |  | Jason and Mario | Yes
TP Training Ambulance community user credentialing reference guide |  | 2018-11-02 |  | Meghan | Yes
TP Training Ambulance provider reference guide |  | 2018-11-02 |  | Meghan | Yes
TP Training Appeals reference guide |  | 2018-11-02 |  | Meghan | Yes
TP Training Claims reference guide |  | 2018-11-02 |  | Meghan | Yes
TP Training Community User Credentialing PP |  | 2018-11-02 |  | Meghan | Yes
TP Training Community User Credentialing reference guide |  | 2018-11-02 |  | Meghan | Yes
TP Training Cultural Competency PP |  | 2018-11-02 |  | Ave | [6 empty] | Where are these docs, not detailed in Provider Handbook
TP Training Denial reasons Claims FAQ |  | 2018-11-02 |  | Meghan | Yes
TP Training ETD reference Guide |  | 2018-11-02 |  | Meghan | Yes
TP Training New provider Training and nesting | 2018-11-01 | 2018-10-30 |  | Meghan | Yes
TP Training Provider Trip management reference guide |  | 2018-11-02 |  | Meghan | Yes
TP Training PTM and ETP PP |  | 2018-11-02 |  | Meghan | Yes
TP Training Reveal driver app reference guide |  | 2018-11-02
TP Training Reveal driver app training PP |  | 2018-11-02
TP Training Reveal Provider portal PP |  | 2018-11-02
TP Training Reveal proviider portal reference guide |  | 2018-11-02
TP Training TP Compliance Training PP |  | 2018-11-02 | 2018-11-26 | Ave | [6 empty] | Where are these docs
Vehicle Inspection and guidelines | 2018-11-01 |  |  | Jason and Mario | Yes
Vehicle inspection form | 2018-11-01 |  |  | Jason and Mario | Yes
VOC Presentation | 2018-11-01 |  | 2018-11-19 | Jason and Mario | No | 2018-11-21 |  |  |  |  | Provided in outreach plan
Website Text |  |  | 2018-11-20 | Meghan | No | 2018-11-21

## Ops Manual
Policy or process | Date due to EOHHS | Date Provided by MTM | Date Reviewed By EOHHS | Reviewed By | Approved? | Date Sent back to MTM | Date Updated Document Received | Date Reviewed | Reviewed By | Approved ? | Notes
Trip Recovery policy
Authorizing and scheduling services
Pre and Post Trip Verification P&P
Peak transportation contingency plan
Denial of service letter |  |  | 2018-11-23 | Meghan | No
Challenging member policy
Attendent/escort policy
Modes of service - Public Transit
Modes of service - Ride Share (Lyft)
Modes of service - Public Motor Vehicle
Modes of service - Multi-Passenger Van
Modes of service - Wheelchair Van
Modes of service - Ambulance (ALS/BLS)
Modes of service - Stretcher Van
Modes of service - Mileage Reimbursement
Modes of service - Volunteer Drivers
Levels of service - Curb to curb
Levels of service - Door to door
TP Monitoring, corrective action, termination |  |  | 2018-11-23 | Meghan | No | [5 empty] | One Edit
TP Training including CPR, HIPAA, Cultural, Defensive driver
TP Credentialing including list of excluded individuals |  |  | 2018-11-23 | Meghan | Yes
Office staff and CCR personnel P&P
Staff training curriculum (not TPs) including mode of transport determination, cultural |  |  | 2018-11-23 | Meghan | Yes
Complaint resolution policy |  |  | 2018-11-23 | Meghan | Yes
Grievance process policy |  |  | 2018-11-23 | Meghan | No
Expedited resolutions of appeals process
Alternative transportation options
Eligibility verification process
Utilization review policy
CCR response standards
Process for TP trip assignment
TP Incentive program
TP Selection criteria
Payment process for TPs
Hours of service 365/24/7
FWA Prevention/investigation |  |  | 2018-11-23 | Meghan | No
TP Contracting
Ambulance Contracting
Relaying TP Issues
TP Help Desk
Re-credentialing Process |  |  | 2018-11-23 | Meghan | No | [5 empty] | One Edit
Post authorization trips
Bus Route entry
Bus Route fare inventory
Provider audit and vehicle inspection
Field Liaisons
Month-end bus reconciliation
Process for short notice trip requests
Performance improvement plan administration
Reporting/handling accidents/incidents
MTM Satisfaction survey
Management of No shows
Quality & Compliance committee/board |  |  | 2018-11-26 | Ave | No | [5 empty] | Title does not reflect content; numbering under Responsibility begins w/#5; where is 1-4,Please review this P&P as it appears there are 2 policies here
Compliance hotline |  |  | 2018-11-26 | Ave | No | [5 empty] | Section #3, what is the significance of KPI as it relates to Hotline
Perforamce improvement plan, TP |  |  | 2018-11-26 | Ave | No | [5 empty] | needs detail when state is notified and time frames
HIPAA Member request compliance |  |  |  | Ave
Document retention |  |  | 2018-11-26 | Ave | Yes
Financial Incentives
Call monitoring/evaluation
Breach of confidentiality process |  |  | 2018-11-26 | Ave | Yes
Client audit management |  |  | 2018-11-23 | Meghan | Yes
Accident/incident escalation process
Publication of members' rights |  |  | 2018-11-23 | Meghan | No
Interaction Handling |  |  | 2018-11-23 | Meghan | No
Cust serv cntr interaction conduct |  |  | 2018-11-23 | Meghan | Yes
Call center service disruption |  |  | 2018-11-23 | Meghan | Yes
Inclement Weather/traffic situations
Recurring appointments
Special Needs transporation scheduling
Translation services |  |  | 2018-11-26 | Ave | No | [5 empty] | need detail re: notifying TPs
Reloadable public transit fare
Member eligibility
Emergency situations
Power outage system failure
Marketing Communications |  |  | 2018-11-26 | Ave | No | [5 empty] | need specificity around LEP, alternative formats, prior approval by state process for member communications Health Literacy should be a comp[anion doc to Marketing Communication
Health Literacy