## Project Status Update
Transportation Transition | [11 empty] | Project Manager: |  |  |  |  | Maria Narishkin
[12 empty] | Today's Date: |  |  |  |  | 2018-11-20
Project Status Update | [11 empty] | Overall Project Status: |  |  |  |  | On Track
Category |  | Status | Project Manager's Notes
Action Items |  | On Track
Schedule |  | On Track
Risks |  | On Track
Issues |  | On Track
Misc. |  | On Track
Anticipated vs. Actual Rate of Completion as of Today (Overall % and Task Count)
Start Date: |  | 2018-08-01 |  |  | Goal Completion Date: |  |  | 2018-12-31 |  | # Days until Goal Completion Date: | [7 empty] | 41
Risks |  |  |  | Issues |  |  |  |  | Questions | [5 empty] | Decisions
Unresolved |  | Resolved |  | Unresolved |  |  | Resolved |  | Unresolved |  | Resolved |  |  |  | Unresolved |  |  | Resolved
1 |  | 0 |  | 0 |  |  | 0 |  | 2 |  | 0 |  |  |  | 0 |  |  | 0
Action Items
Total |  | Complete |  | In Progress |  |  | Not Yet Due |  | Unknown |  | Blocked |  |  |  | Incomplete |  |  | Overdue
91 |  | 29 |  | 16 |  |  | 26 |  | 9 |  | 0 |  |  |  | 1 |  |  | 10
# | Objectives & Deliverables | [12 empty] | O / D | # Related Tasks |  |  | Tasks Complete
[18 empty] | # | %
1 | Systems implementation and data transfers (LogistiCare, MTM and EOHHS) | [12 empty] | D | 6 |  |  | 0 | 0%
2 | Transportation network adequacy and access | [12 empty] | O | 11 |  |  | 2 | 18.18%
3 | Policies and Procedures, Requirements, Compliance and Reporting | [12 empty] | D | 42 |  |  | 7 | 16.67%
4 | Stakeholder Engagement/Communications | [12 empty] | D | 28 |  |  | 2 | 7.143%
5 | Broker requirements | [12 empty] | O | 23 |  |  | 17 | 73.91%
6 | Operations | [12 empty] | D | 12 |  |  | 1 | 8.333%
7 | EOHHS Financial | [12 empty] | O | 5 |  |  | 0 | 0%
8 | Regulations and Policy | [12 empty] | D | 2 |  |  | 0 | 0%
Role | [5 empty] | Project Member Name | [6 empty] | Agency |  |  | Decision Rights
EOHHS Deputy Director | [5 empty] | January Angeles | [6 empty] | EOHHS |  |  | Approval Required
Project Lead | [5 empty] | Kristin Sousa | [6 empty] | EOHHS |  |  | Approval Required
Stakeholder Engagement/Systems | [5 empty] | Marlanea Peabody | [6 empty] | EOHHS |  |  | Consulted
Project Manager | [5 empty] | Maria Narishkin | [6 empty] | EOHHS
Transportation Team Lead | [5 empty] | Jason Lyon | [6 empty] | EOHHS
Transportation Team Manager | [5 empty] | Mario Olivieri | [6 empty] | EOHHS
Stakeholder Engagement | [5 empty] | Brenna McCabe and Diana Beaton | [6 empty] | EOHHS
Policy and Compliance | [5 empty] | Meghan Ruane and Ave Houston | [6 empty] | EOHHS
Impact Goal:
Implementation of new vendor contract including readiness and operations for the Medicaid non-emergency Medical Transportation program, the Elderly Transportation Program and transportation for TANF recipients
Opportunity Statement:
Anticipated Risks & Obstacles | [8 empty] | Key Performance Indicators
1 | LGTC not cooperating with transition | [7 empty] | 1
2 | [8 empty] | 2
3 | [8 empty] | 3
4 | [8 empty] | 4
Note on I6: If On Track, What are the most critical action items coming up? If Off Track, what are the the most critical action items to get back on track? If At Risk, what action items must be completed?
Note on I7: Is the project on schedule to hit its targets? If the goal of the "project" is to reach an outcome goal, are the metrics on track? If the project has a defined end point, have action items been completed in a timely manner?
Note on I8: What problems to achieving the project end or metrics may be encountered? What should the project lead focus on mitigating and how should it be done?
Note on I9: What challenges is the project currently facing? How should they be overcome?
Note on I10: What else should the project lead know about progress?
Note on A11: If the project manager is using the action item tab, this graph will automatically update to show actual project progress vs. anticipated project progress.
Note on A14: If the project manager is using the "Risks & Issues" tab, this will automatically update to show resolved and unresolved risks
Note on Q14: If the project manager is using the "Risks & Issues" tab, this will automatically update to show resolved and unresolved issues
Note on AG14: If the project manager is using the "Questions & Decisions" tab, this will automatically update to show resolved and unresolved questions
Note on AW14: If the project manager is using the "Questions & Decisions" tab, this will automatically update to show resolved and unresolved decisions
Note on C20: This part of the project charter should be used to highlight the work that needs to be performed by the team. For example, it could be gathering data and preparing an anlaysis, develoing and evaluation strategy, submitting a budget article. What written work or other concrete deliverable will the project accomplish?
Note on AT20: Objective or Deliverable
Note on AW20: If you are using the "Action Items" tab, include the corresponding objective or deliverable # in each action item, and this section will automatically update.
Note on A30: For each person on the project, why are they on the project? What contribution are they expected to make?
Note on BA30: Who is empowered to make decisions for the project? Who has the power to say yes?
Note on A39: What is the project trying to achieve? When this goal is achieved, the proejct will be closed (e.g. Launch website, reduce backlog to 10% of total applications, win $1m in grant funding)
Note on A41: Why is this project worth undertaking? What opporutnity does the group have to seize?
Note on A43: What does the group see as likely challenges that should be mitigated from the beginning of the project?
Note on AG43: What metrics will the project collect to know if it is being successful? At least some should be collected weekly to know that short term actions are having intended effects.

## Additional PM Notes
Please use this space to report qualitiative updates.
Progress:
Data from LGTC - going to stakeholder, discuss with stakeholders to have stakeholders discuss with logisticare. Can we get some information from TPs Open medical necessity for 6 months - no check needed List of all providers from DXC - Marlanea will send email Past 3 month history extract - to be used for volume for adequate network and to prepopulate Toll free numbers - Slide with a missing phone number. New phone number effective 12/18. Get a number by next week. Transition language in amendment. Get encounter data Get phone number - quick turn around, we can wait until next week. Communication about phone number by the end of November (stakeholder) Get info from facilities Meeting being set up with RIPTA for RIPTA bus pass plan (Wednesday) Ombudsman request - 1st quarter January ok with that
New Issues or Stalled Action Items:
Have there been meetings or communication with MTM's Reveal Team?
Cross-Agency Impact:
[Test text]
Escalations Suggested:
[Test text]

## Action Items
# | Action Item | Reason | Objec/ Deliv | Accountable | Support | Origin | Created | Start | Due | Done | Status | Notes | . | Type of document/ proof of compliance | Document Name | Date Due to EOHHS | Date Provided by MTM | Date Reviewed By EOHHS | Reviewed By | Approved? | Date Sent back to MTM | Date Updated Document Received | Date Reviewed | Reviewed By | Approved ? | Notes
5.01 | Receive Performance Bond |  | 5 | Purchasing | Mario |  | 2018-09-26 | 2018-08-16 | 2018-08-16 |  | Complete | Submitted with proposal |  | Certification |  | 2018-12-01 |  |  |  | Yes
5.02 | Receive Broker Professional Liability Insurance |  | 5 | Purchasing | Mario |  | 2018-09-26 | 2018-08-16 | 2018-08-16 |  | Complete | Submitted with proposal |  | Certification |  | 2018-12-01 |  |  |  | Yes
5.03 | Receive Broker Workers' Compensation insurance |  | 5 | Purchasing | Mario |  | 2018-09-26 | 2018-08-16 | 2018-08-16 |  | Complete | Submitted with proposal |  | Certification |  | 2018-12-01 |  |  |  | Yes
5.04 | Receive Broker automobile Liability |  | 5 | Purchasing | Mario |  | 2018-09-26 | 2018-08-16 | 2018-08-16 |  | Complete | Submitted with proposal |  | Certification |  | 2018-12-01 |  |  |  | Yes
5.05 | Staffing Implementation Plan |  | 5 |  |  |  | 2018-09-26 | 2018-09-30 | 2018-10-15 | 2018-09-30 | Complete | Received |  | Written Attestation | Staffing plan | 2018-11-01 | 2018-09-25 |  |  | Yes | [5 empty] | Submitted with Contract
3.03 | Review FWA policy |  | 3 | Tom Bouchard | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-01 |  | Complete | Received FWA plan, EOHHS Approved Meghan sent a list of P&Ps referenced in the FWA integrity plan |  | P&P | FWA Integrity Plan | 2018-11-21 |  |  | Tom Bouchard | Yes
5.07 | Ensure broker is licensed in RI | Contract Compliance | 5 | Jason | Mario |  | 2018-09-01 | 2018-11-01 | 2018-11-01 |  | Complete | Received MTM RI Cert of good standing |  | License | MTM RI Cert of Good Standing | 2018-11-01 |  |  |  | Yes
5.08 | Ensure broker is registered as a state vendor | Contract Compliance | 5 | Jason | Mario |  | 2018-09-01 | 2018-11-01 | 2018-11-01 |  | Complete | Received MTM RI Enrollment Status |  | Registration / Written Attestation | MTM RI Enrollment Status | 2018-11-01 |  |  |  | Yes
5.26 | Review and approve Implementation Plan | Operations/transition | 5 | Jason | Mario |  | 2018-09-26 | 2018-10-15 | 2018-11-01 |  | Complete | Received implementation plan (MTM Project Plan) |  | Written Attestation | RI NEMT Implementation | 2018-10-15 | 2018-09-01 |  |  | yes
5.09 | Review and approve key management positions to be located in RI | Contract Compliance | 5 | Jason | Mario |  | 2018-08-09 | 2018-09-30 | 2018-11-01 | 2018-09-30 | Complete | Staffing plan submitted with contract |  | Written Attestation | Staffing plan | 2018-11-01 | 2018-09-25 |  |  | Yes | [5 empty] | Submitted with Contract
2.03 | Approve TP contract template |  | 2 | Jason | Mario |  | 2018-09-26 |  | 2018-11-01 |  | Complete | DPUC Standards must be in contract |  | Contract |  | 2018-11-01 |  |  |  | Yes
5.06 | Identify office location | Ensure the location complies with contract requirements | 5 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-01 |  | Complete | Received trade name certificate Do we have copy of lease? |  | Lease |  | 2018-11-01 |  |  |  | Yes
2.04 | TP contracts executed |  | 2 | Jason | Mario Ave |  | 2018-09-26 | 11/1/18* | 2018-11-01 |  | In Progress | * Requires weekly updates |  | Contracts |  | Weekly Updates
4.01 | Review and approve partner/stakeholder/facility communications and engagement | Stakeholder engagement | 4 | Brenna | Diana |  | 2018-09-26 | 2018-11-01 | 2018-11-07 |  | Overdue | Received communication and education plan, facility intro letter, MTM overview presentation and slides 11/16 Communication and education plan is with communications team, 11/18 Maria requests completion by COB 11/19 |  | Plan | Comm & Education Plan, Facility Implementation, Town Hall sign-in, Facility intro letter, MTM Overview presentation, State Resource guide | 11/1/2018 11/1/2018 |  |  |  | No Comm/ed plan with Comm team | 2018-11-16 |  |  |  |  | 11/19 Jason sent comments to MTM on Presentation
3.05 | Review forms and P&P for Pre-trip verification |  | 3 | Jason | Ave Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 |  | Complete | Received pre-trip inspection report, vehicle inspection report and guidelines - EOHHS Approved |  | P&P | Daily pre-trip inspection report | 2018-11-01 |  |  |  | Yes
3.38 | Review and approve written material | Marketing material review | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 |  | Overdue | Received RI ACA Language insert 11/16 Sent back to MTM with edits |  | As Documented | RI ACA Language Insert | 2018-11-01 |  |  |  | No | 2018-11-16
3.37 | Review and approve broker marketing materials | Marketing material review | 3 | Brenna | Diana |  | 2018-09-26 | 2018-11-01 | 2018-11-07 |  | Overdue | Received RI postcard and Website text 11/18 Maria requests completion by COB 11/19 |  | As Documented | RI Postcard Text, RI Website Text | 2018-11-01 |  |  | Brenna, Diana
6.08 | EOHHS to provide contact information and ensure connection between MTM and MCOs for coordination of services with MCOs | Stakeholder engagement | 6 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 |  | Overdue | Provided in outreach plan - MCOs are not specifically mentioned in the outreach plan but MTM includes MCOs as part of their outreach plan when directed by client |  | Written Attestation | Same as 4.01 plus: VOC Presentation | 2018-11-01 | [9 empty] | Provided in outreach plan
4.03 | Dialysis Meeting | MTM Meet & Greet | 4 | Mario |  |  | 2018-11-09 | 2018-11-07 | 2018-11-07 | 2018-11-07 | Complete
6.09 | EOHHS to provide contact information and ensure connection between MTM and AEs for coordination of services withCoordination of services with AEs | Stakeholder engagement | 6 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 |  | Overdue | Provided in Outreach Plan - Identify Key Stakeholders (Advocacy Groups/Legislators/NEMT Advisory Committee), Federally Recognized Tribes, Refugee Populations, Health Care Providers, Provider Associations, Community Base Organizations, Consumer Representatives Discuss with EOHHS any special needs groups – MTM |  | Written Attestation |  | 2018-11-01
6.1 | EOHHS to provide contact information and ensure connection between MTM and RIPTA for coordination of services with RIPTA's RIde Program | Stakeholder engagement | 6 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 |  | Overdue | Establish contact and open communication with public transit entities/ADA para-transit providers, escalate information to Network Management Community Outreach collaborates with Logistics to provide necessary information regarding fixed route and ADA information. - MTM Discuss at 11/16 RIPTA meeting |  | Written Attestation |  | 2018-11-01
6.11 | EOHHS to provide contact information and ensure connection between MTM and high-utilizing providers for coordination of services with high-utilizing providers (Adult day, Dialysis, SUD, etc.) | Stakeholder engagement | 6 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 |  | Overdue | Identify contact information for dialysis and other medical facilities. Community Outreach is researching and establishing contact information for medical facilities during implementation. Proactive outreach via phone, web sessions, email and on-site will continue through the life of the contract. – MTM |  | Written Attestation |  | 2018-11-01
4.24 | Managed Care Organizations & Dental Meeting | Update, as needed | 4 | January and Kristin |  |  | 2018-11-09 |  | 2018-11-13 |  | Overdue | As needed
6.01 | EOHHS Meeting with RIPTA | Bus Pass technology | 6 | Jason | January Kristin |  | 2018-11-08 |  | 2018-11-14 |  | Complete
4.05 | Long Term Care Coordinating Council (LTCCC) Meeting | Transition Update | 4 | Marlanea, Jason, Mario, Mike |  |  | 2018-11-09 |  | 2018-11-14 |  | Unknown | Confirmed
3.33 | Verify CCRs' multilingual capacity |  | 3 |  | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-15 |  | Complete | Received language attestation doc |  | Written Attestation | Language Attestation | 2018-12-15 |  |  |  | Yes
4.06 | Substance Use and Leadership Council Meeting | MTM Meet-and-Greet/Overview | 4 | Marlanea, Jason, Mike |  |  | 2018-11-09 |  | 2018-11-15 |  | Complete | 9-10:30 am
2.05 | Monitor and ensure TP supply adequacy | Operations | 2 | Jason | Mario |  | 2018-09-26 | 11/15* | 2018-11-15 |  | In Progress | * Requires weekly updates |  | List of contracted TPs with Details |  | Weekly Written Updates
2.06 | Monitor and review GEO access map form MTM |  | 2 | Jason | Mario |  | 2018-11-09 | 11/15* | 2018-11-15 |  | With Vendor | * Requires weekly updates |  | GeoAccess Map |  | Weekly Updates
2.08 | Provide encounter Data to MTM | MTM to use for provider recruitment effort | 2 | Marlanea | Steve DXC |  | 2018-09-26 |  | 2018-11-16 |  | Complete | DXC is preparing data 11/16 5 encounter files were sent to DXC with member information
2.07 | Provide current usage member data from LGTC to MTM |  | 2 | Marlanea | Steve DXC |  | 2018-09-26 |  | 2018-11-16 |  | Overdue
2.1 | Get list of all medical providers from DXC | To provide data to MTM | 2 | Marlanea | Steve DXC |  | 2018-11-09 | 2018-11-14 | 2018-11-16 |  | Overdue | Marlanea to email request to DXC 11/19 Jason sent contact files
4.07 | Assisted Living Providers Meeting | MTM Meet-and-Greet/Overview | 4 |  |  |  | 2018-11-09 |  | 2018-11-16 |  | Unknown
4.11 | Internal email to EOHHS, BHDDH, DEA, DHS staff meeting | Transition overview | 4 |  |  |  | 2018-11-09 |  | 2018-11-19 |  | Unknown | Signed by Patrick
3.4 | Review and approve member material | Stakeholder engagement | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-15 | 2018-11-20 |  | In Progress |  |  | As documented | List of documents on weekly operations agenda | 2018-11-15 | 2018-11-12
4.08 | Stakeholder/Advocate Meeting | MTM Meet-and-Greet/Overview | 4 |  |  |  | 2018-11-09 |  | 2018-11-20 |  | Not Yet Due
3.39 | Review and approve recipient communications | Marketing material review | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-21 |  | In Progress | 10/30/18 waiting approval on communications material and member file |  | As Documented |  | 2018-11-01
6.03 | Transfer of toll-free number(s) from LGTC to MTM or acquire new numbers | Operations | 6 | Marlanea | Jason |  | 2018-09-26 | 2018-11-16 | 2018-11-21 |  | In Progress | Marlanea to confirm acquisition of new toll free number with MTM by 11/14 11/19 LGTC/MTM/EOHHS conference call. LGTC will transfer main reservation number to MTM. Number to port on 12/17 at 6PM. Jason following up on TDD number transition. LGTC to send port form by 11/20 and will get temporary number for 12/18-12/31. LGTC will send language for approval for post 1/1 |  | Written Attestation |  | 2018-12-15
2.09 | ADA Eligibility RIPTA database sharing | Eligibility Verification | 2 | Marlanea | Steve DXC |  | 2018-09-26 |  | 2018-11-21 |  | Incomplete | Discuss during meeting with RIPTA 11/21
1.12 | Set up weekly meeting with EOHHS and LGTC |  | 1 | Jason | Mario |  |  | 2018-11-19 | 2018-11-21 |  | In Progress | Jason to contact LGTC for scheduling
3.41 | Review TANF Rules |  | 3 | Mario |  |  |  | 2018-11-19 | 2018-11-21 |  | In Progress | Mario to look into TANF Policy and rules for bus pass distribution to member or entire household.
6.1 | RIPTA and MTM Meeting |  | 6 | Jason | Mario |  |  | 2018-11-21 | 2018-11-21 |  | Not Yet Due | Bus pass distribution, Jason is setting up meeting
4.13 | Adult Day Meeting | MTM Meet-and-Greet/Overview | 4 |  |  |  | 2018-11-09 |  | 2018-11-26 |  | Not Yet Due
4.14 | EOHHS Task Force Meeting | Update, if asked | 4 |  |  |  | 2018-11-09 |  | 2018-11-26 |  | Not Yet Due | Confirmed
3.01 | Staffing P&P Review | Contract Compliance | 3 |  | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | Complete | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P | Compliance plan | 2018-11-01 |  |  |  | Yes | [5 empty] | Provided 2018 Compliance Plan
3.22 | Review and approve TP manual |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | Complete | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P | RI Provider Handbook | 2018-11-21 |  |  | Meghan | Yes
5.23 | MTM to consider employing from RI Works, RI Unemployment, M/WBE (P&P) | Staffing | 5 | Jason | Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | Lissa to touch base with Kim Rauch. MTM MTM asking for clarification on unemployment, MTM requested extention for delivery of this manual, approved by EOHHS 10/30/18 |  | P&P | RI Works Contracts and Recruiting Info | 2018-11-01 | 2018-11-16 | [8 empty] | Still need Unemployment/M/WBE
4.15 | Home Care Meeting | MTM Meet-and-Greet/Overview | 4 |  |  |  | 2018-11-09 |  | 2018-11-28 |  | Not Yet Due
2.01 | Review and approve TP selection criteria |  | 2 | Jason | Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
2.02 | Review process for making payments to TPs |  | 2 | Jason | Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.02 | Review and approve trip recovery policy |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.04 | Review MTM process for authorizing and scheduling services |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.06 | Review forms and P&P for post-trip verification |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.07 | Review P&P on contingency plans for unexpected peak transportation demands |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.08 | Denial of Service Determination P&P Review | Eligibility | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM Approval from EOHHS 10/30/18 |  | P&P |  | 2018-11-21
3.09 | Review/approve challenging member P&P | Contract Compliance | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM Approval from EOHHS 10/30/18 |  | P&P |  | 2018-11-21
3.1 | Review/approve attendant (escort) policy | Contract Compliance | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM Approval from EOHHS 10/30/18 |  | P&P |  | 2018-11-21
3.11 | Review P&P for all modes of service listed in comments section | Contract Compliance | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | Public transit, ride-share, PMV, Multi-passenger van, wheelchair van, ambulance (stretcher van, ALS, BLS), mileage reimbursement, volunteer drivers 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM Approval from EOHHS 10/30/18 |  | P&P |  | 2018-11-21
3.12 | Review P&P for levels of service (Door-to-door and curb-to-curb) | Contract Compliance | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM Approval from EOHHS 10/30/18 |  | P&P |  | 2018-11-21
3.13 | Review and approve P&P for TP monitoring, corrective action, termination… |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.15 | Review and approve P&P for TP credentialing including background checks, review of CMS's List of Excluded Individuals and the System for Award Management |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | Added requirements in action item at left 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.16 | Review and approve P&P for personnel including office staff and CCRs |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.17 | Review and approve staff training curriculum |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.18 | Review and approve Complaint resolution policy |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.19 | Review and approve Grievance process policy |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.2 | Review and approve expedited resolutions of appeals process |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.21 | Review and approve P&P for alternative transportation options |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.23 | Review and approve Quality Assurance data and reporting |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.24 | Review and approve Quality Improvement and operations plan |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | Received Compliance Program Plan 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.25 | Review and approve utilization review policy |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.26 | Review eligibility verification process | Eligibility | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM Approval from EOHHS 10/30/18 |  | P&P |  | 2018-12-01
3.41 | Review and approve TP Incentive Program P&P |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.36 | Review proposed report templates and ensure they meet contract requirements |  | 3 | Jason | Mario Meghan |  | 2018-09-26 | 2018-11-21 | 2018-11-28 |  |  | Includes: financial statements, recipient satisfaction surveys, FWA, recovery, performance, complaints, grievances and appeals, trips by LOB… |  | P&P |  | 2018-11-21 | 2018-11-15
4.18 | Nursing Homes Meeting | MTM Meet-and-Greet/Overview | 4 |  |  |  | 2018-11-09 |  | 2018-11-29 |  | Not Yet Due
3.14 | Review and approve P&P for TP training (includes CPR, HIPAA, Cult Comp, Def Driver…), training material, training events… |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-15 | 2018-12-01 |  | In Progress | 10/30/18 Added transportation training materials and nesting plan |  | P&P | New provider Training and nesting, Provider taining materials.zip | 2018-11-01 | 2018-10-30
7.02 | Ensure pathway to send capitation payments for Medicaid members to MTM | Finance | 7 | Marlanea | Kathy Corsino |  | 2018-09-26 |  | 2018-12-01 |  | In Progress
7.03 | Ensure pathway to send payments for the ETP program | Finance | 7 | Marlanea | Kathy Corsino |  | 2018-09-26 |  | 2018-12-01 |  | In Progress
7.04 | Ensure pathway to send payments for TANF program | Finance | 7 | Marlanea | Kathy Corsino |  | 2018-09-26 |  | 2018-12-01 |  | In Progress
1.13 | Review TP Claims processing function |  | 1 | Marlanea | Steve DXC |  | 2018-09-26 |  | 2018-12-01 |  | Not Yet Due
7.01 | Ensure pathway for assessing liquidated damages to Broker | Finance | 7 | Mario | Kathy Corsino |  | 2018-09-26 |  | 2018-12-01 |  | Not Yet Due | EOHHS granted 180 day grace period from start of contract
4.19 | FQHCs Meeting | Transition update | 4 |  |  |  | 2018-11-09 |  | 2018-12-03 |  | Not Yet Due
4.2 | Children’s Services Providers Meeting | MTM Meet-and-Greet/Overview | 4 |  |  |  | 2018-11-09 |  | 2018-12-04 |  | Not Yet Due
3.32 | Review and approve Quality Assurance Policy |  | 3 |  | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-05 |  | Complete | Received Policy, EOHHS Approved |  | P&P | 2018 Quality Assurance Program | 2018-12-01 |  |  |  | Yes
3.27 | Review TP permits, licenses, insurance |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-05 |  | With Vendor |  |  | Written Attestation | TP Appendix B | 2018-11-15 | 2018-11-12
1.03 | Test enrollment file transfer for Medicaid Eligibility (834) | Eligibility | 1 | Marlanea | Steve DXC |  | 2018-09-26 | 2018-12-01 | 2018-12-05 |  | In Progress | MTM is setting up a SFTP site for file transfers. 11/16 DXC check to see if it was received and MTM will send a list of questions by end of day. |  | Written Attestation |  | 2018-12-01
1.04 | Test enrollment file transfer for TANF Eligibility | Eligibility | 1 | Marlanea | Steve DXC - Steve Fugate |  | 2018-09-26 | 2018-12-01 | 2018-12-05 |  | In Progress | Potential DHS removal of program from brokerage, MTM is setting up a SFTP site for file transfers Steve is communicating with MTM re: questions on TANF files |  | Written Attestation |  | 2018-12-01
2.11 | Data sharing from LGTC to MTM |  | 2 | Marlanea | Steve |  |  | 2018-11-15 | 2018-12-05 |  | In Progress | 11/16 LGTC has template to use for sharing Elderly files and standing orders
1.05 | Review P&P for retroactive eligibility claims processing |  | 1 | Marlanea | Steve DXC |  | 2018-09-26 | 2018-12-01 | 2018-12-05 |  | Not Yet Due |  |  | P&P |  | 2018-12-01
4.21 | Hospitals/HARI Meeting | MTM Meet-and-Greet/Overview | 4 | Mike C. |  |  | 2018-11-09 |  | 2018-12-06 |  | Not Yet Due
5.14 | Receive Broker insurance endorsement |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | Complete |  |  | Certification | MTM Certificates of insurance | 2018-12-01 |  |  | Jason | Yes | [5 empty] | 11.12.18: sent clarification 11.9.18 on the intent of this certification. Based on MTM legal review, MTM attested to this by signing the contract.
5.15 | Receive Broker Comprehensive Liability Insurance |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | Complete |  |  | Certification | MTM Certificates of insurance | 2018-12-01 |  | Jason |  | Yes | [5 empty] | 11.12.18: sent clarification 11.9.18 on the intent of this certification. Based on MTM legal review, MTM attested to this by signing the contract.
5.16 | Receive Broker Property Damage Insurance |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | Complete |  |  | Certification | MTM Certificates of insurance | 2018-12-01 |  | Jason |  | Yes | [5 empty] | 11.12.18: sent clarification 11.9.18 on the intent of this certification. Based on MTM legal review, MTM attested to this by signing the contract.
5.17 | Receive Broker Errors and Omissions insurance |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | Complete |  |  | Certification | MTM Certificates of insurance | 2018-12-01 |  | Jason |  | Yes | [5 empty] | 11.12.18: sent clarification 11.9.18 on the intent of this certification. Based on MTM legal review, MTM attested to this by signing the contract.
5.19 | Broker's disclosure of ownership and control interest |  | 5 | Jason | Ave Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | Complete |  |  | Written Attestation | RI Disclosure of Ownership | 2018-12-01 |  |  |  | Yes
3.28 | Review and approve P&P for TP vehicle compliance including PUC license, ADA compliance and vehicle inspection process and forms |  | 3 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-12-07 |  | Complete | Received vehicle inspection guidelines and inspection form |  | P&P | Vehicle Inspection and guidelines, RI vehicle inspection form | 2018-11-01 |  |  |  | Yes | [5 empty] | Must still approve vehicle inspection form
5.12 | Receive Broker certification of truthfulness |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | Complete |  |  | Certification | Warranties section of contract | 2018-12-01 |  | Jason |  | Yes | [5 empty] | 11.12.18: sent clarification 11.9.18 on the intent of this certification. Based on MTM legal review, MTM attested to this by signing the contract.
5.13 | Receive Broker certification of Legality |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | Complete |  |  | Certification | Warranties section of contract | 2018-12-01 |  | Jason |  | Yes | [5 empty] | 11.12.18: sent clarification 11.9.18 on the intent of this certification. Based on MTM legal review, MTM attested to this by signing the contract.
3.29 | Review and approve CCR training including operational (mode of transport determination, scheduling…) and interpersonal (cultural/disability sensitivity) |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | Not Yet Due |  |  | P&P |  | 2018-12-01
3.3 | Review and approve CCR response standards for member, facilities and TP services |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | Not Yet Due |  |  | P&P |  | 2018-12-01
3.31 | Review process for TP trip assignment |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | Not Yet Due |  |  | P&P |  | 2018-12-01
5.11 | Ensure RI operation is fully staffed (written attestation) | Contract Compliance | 5 | Jason | Ave Meghan |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | With Vendor | Concern with CCRs working from home. 10/30/18 MTM CCR staff will be located onsite at RI office. 1st training class slated for 11/12/18 Concern with HIPAA and privacy for remote people. Need clear policies. |  | Written Attestation |  | 2018-12-01
5.18 | Ensure Broker's ability to maintain confidential information (written attestation) |  | 5 | Jason | Ave Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | With Vendor |  |  | Written Attestation |  | 2018-12-01
5.24 | Ensure Broker's ability to maintain records for 10 years (written attestation) |  | 5 | Jason | Ave Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | With Vendor |  |  | Written Attestation |  | 2018-12-01
6.02 | Review and approve MTM Website (written attestation) | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | With Vendor |  |  | Written Attestation |  | 2018-12-01 | [9 empty] | 11.12.18: MTM will develop a stakeholder-facing informational website, www.mtm-inc.net/rhode-island, dedicated exclusively to Rhode Island’s NEMT, TANF, and ETP programs. The website will include the procedures required to request services, complaint and appeal procedures, riders’ rights and responsibilities, contact information, and other pertinent program details. Content will be approved by EOHHS prior to going live.
6.04 | Review and approve Mobile Apps (written attestation) | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | With Vendor |  |  | Written Attestation |  | 2018-12-01
4.09 | Stakeholder/Advocate Meeting | Transition update | 4 |  |  |  | 2018-11-09 |  | 2018-12-11 |  | Not Yet Due
4.22 | Long-Term Care Coordinating Council (LTCCC) Meeting | Transition Update | 4 |  |  |  | 2018-11-09 |  | 2018-12-12 |  | Not Yet Due | Confirmed
4.23 | EOHHS Task Force Meeting | Transition Update | 4 |  |  |  | 2018-11-09 |  | 2018-12-17 |  | Not Yet Due | Confirmed
5.1 | Ensure hours of service are 365, 24/7 | Contract Compliance | 5 | Jason | Ave Mario |  | 2018-09-26 | 2018-12-15 | 2018-12-17 |  | With Vendor | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM Approval from EOHHS 10/30/18 |  | P&P |  | 2018-11-21
4.26 | Meeting with All Other Providers (Waiver Group)/Personal Choice/Care Mgmt |  | 4 |  |  |  | 2018-11-09 |  | 2018-12-18 |  | Not Yet Due
6.05 | Ensure availability of Telephone Device for the Deaf (TDD) | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-15 | 2018-12-18 |  | With Vendor | 11/19 MTM Stated that they use global 711 for this service |  | Written Attestation |  | 2018-12-15
6.06 | Ensure Automatic call distributor (ACD) is operational (written attestation) including call flow routing, call tracking and call extraction and reporting | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-15 | 2018-12-18 |  | With Vendor |  |  | P&P |  | 2018-12-15
6.07 | Verify that telephone backup system is operational (written attestation) | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-15 | 2018-12-18 |  | With Vendor |  |  | Written Attestation |  | 2018-12-15
8.01 | Promulgation of Transportation Policy | State Policy | 8 | Tarah Provencal | Mario |  | 2018-09-26 | 2018-11-13 | 2018-12-31 |  | In Progress | 11/13 Mario and Jason to send answers to stakeholder questions to January for review 11/19 Updated complete tracked changes regs sent to January
8.02 | CMS Approval of Transportation SPA | State Plan | 8 | Melody Lawrence | Mario |  | 2018-09-26 |  | 2018-12-31 |  | In Progress | 11/19 Maria emailed Mel for update, CMS is waiting for final pages and will send the approval letter.
4.28 | Long-Term Care Coordinating Council (LTCCC) Meeting | Transition Update | 4 |  |  |  | 2018-11-09 |  | 2019-01-09 |  | Not Yet Due | Confirmed
3.34 | Ensure broker's audit capacity and compliance per contract (P&P) |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2019-01-01 | 2019-01-10 |  | Not Yet Due |  |  | P&P |  | 2019-01-01
4.1 | Stakeholder/Advocate Meeting | TBD | 4 |  |  |  | 2018-11-09 |  | 2019-01-10 |  | Not Yet Due
4.29 | EOHHS Task Force Meeting | Transition Update | 4 |  |  |  | 2018-11-09 |  | 2019-01-28 |  | Not Yet Due | Confirmed
7.05 | Approve MTM financial reporting policy and templates | Finance | 7 | Mario | Kathy Corsino |  | 2018-09-26 | 2019-02-01 | 2019-02-10 |  | Not Yet Due |  |  | P&P |  | 2019-02-01
5.22 | Broker's Ombudsman to be located in Rhode Island by end of 2019 Q1 | Staffing | 5 | Jason | Ave Mario |  | 2018-11-09 | 2018-11-09 | 2019-03-31 |  | Not Yet Due | State approved broker's ombudsman to be located in RI by end of 2019 Q1
3.35 | Ensure compliance on AVL Capacity for vehicles (Written Attestation) |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2019-04-01 | 2019-04-08 |  | With Vendor | EOHHS granted 90 day grace period from start of contract |  | Written Attestation |  | 2019-04-01
1.08 | Test and verify broker's ability for 837 Encounter data submission |  | 1 | Marlanea | Steve DXC |  | 2018-09-26 | 2019-04-01 | 2019-04-30 |  | Not Yet Due | Not started, will complete after go-live in the spring
[15 empty] | Audit Recoupment Letter |  |  |  |  | Yes
[15 empty] | Disaster Recovery |  | 2018-11-19 | 2018-11-19 | Ave | Yes | [5 empty] | Sent in lieu of staffing plan
[15 empty] | Generic RFI |  |  |  |  | Yes
[15 empty] | GMR Trip Log doc |  |  |  |  | Yes
[15 empty] | Incidient/Accident Report form |  |  |  |  | Yes
[15 empty] | Level of Need - Ambulance |  |  |  |  | Yes
[15 empty] | Level of Need - Standard |  |  |  |  | Yes
[15 empty] | Bus Letter |  | 2018-11-19 | 2018-11-19 | Meghan | No | 2018-11-19
[15 empty] | MTM Curency Welcome Letter - no public transit |  | 2018-11-19 | 2018-11-19 | Meghan | No | 2018-11-19 | 2018-11-19
[15 empty] | MTM Incoming call guide |  |  |  |  | Yes
[15 empty] | MTM Provider Audit |  |  |  |  | Yes
[15 empty] | TP Helpdesk |  | 2018-11-12
4.04 | Consumer Advisory Committee Meeting |  | 4 |  |  |  | 2018-11-09 |  |  |  | Unknown
4.12 | Federally recognized tribes Meeting | MTM Meet-and-Greet/Overview | 4 |  |  |  | 2018-11-09 |  |  |  | Unknown
4.16 | DEA Providers Meeting | MTM Meet-and-Greet/Overview | 4 |  |  |  | 2018-11-09 |  |  |  | Unknown
4.17 | Senior Centers Meeting | MTM Meet-and-Greet/Overview | 4 |  |  |  | 2018-11-09 |  |  |  | Unknown
4.25 | MTM Town Hall Meeting | General Information (MTM) | 4 |  |  |  | 2018-11-09 |  |  |  | Unknown
4.27 | DXC Listservs Meeting |  | 4 |  |  |  | 2018-11-09 |  |  |  | Unknown

## Risks & Issues
# | Risk / Issue | Origin | Date Created | Date Due | Description | Mitigation Plan | Primary Owner | Status | Notes
1.01 | Risk | 11/9 Internal Meeting | 2018-11-09 | 2018-11-16 | LGTC not providing member files | Acquire information from encounter data and facilities, open medical necessity for 3 or 6 months |  | In Progress | Marlanea is lead in systems

## Questions & Decisions
# | Question / Decision | Origin | Date Created | Date Due | Description | Outcome | Primary Owner | Status | Notes
1 | Question | 11/8 MTM Meeting | 2018-11-08 | 2018-11-30 | 10% pre and post verification partnering with EOHHS - what is the timeline for post-trip verification - change the percentage |  |  | Unresolved | 10% would take 4 full-time positions, can we decrease the percentage or give encounter data to MTM to use for trip verification
1.01 | Question | Maria | 2018-11-09 |  | Have there been meetings or communication with MTM's Reveal Team?

## Project Metrics (hidden)
Metric # | Metric | Definition | Data Source | Person Responsible | Target Value | Target Goal | Target Date | Frequency | 2018-09-16 | 2018-09-23 | 2018-09-30 | 2018-10-07 | 10/14/2018 | 10/21/2018 | 10/28/2018 | 11/4/2018
1 | # of Overdue Applications in State Hands | # of applications pending after receipt from client that are workable by the State for more than 90 days | RIB Tableau KPI | XYZ |  |  |  | Weekly

## Data Validation (hidden)
Status | Project Manager | AI Status | QRID Status | Frequency | Agency | Decision Rights | Anticipated vs. Actual Completed by Today's Date
On Track | Jasper Frank | Blocked | Blocked | Daily | BHDDH | Approval Required | Start Date: | 2018-08-01
At Risk | Catherine Gering | Complete | In Progress | Weekly | DCYF | Consulted | Today's Date: | 2018-11-20
Off Track | Matt Kiehnle | In Progress | Not Yet Due | Monthly | Deloitte | N/A | End Date: | 2018-12-31
Other | Maria Narishkin | Incomplete | Overdue | Quarterly | DHS |  |  | Anticipated | Actual
|  | Not Yet Due | Resolved |  | EOHHS |  | Complete | 36 | 3
|  | Overdue | Unknown |  | HSRI |  | Incomplete | 55 | 88
|  | Unknown | Unresolved |  | Medicaid |  |  | 39.56% | 3.297%
|  | With Vendor | With Vendor |  | Other
RIDOH
|  | Total | Total
|  | Complete | Resolved |  |  |  | Total Tasks | 91
|  | In Progress | In Progress
|  | Not Yet Due | Not Yet Due
|  | Unknown | Unknown
|  | Blocked | Blocked
|  | Incomplete | Unresolved
|  | Overdue | Overdue
Risks
Issues
Questions
Decisions