## Project Status Update
Transportation Transition | [16 empty] | Project Manager: |  |  |  |  | Maria Narishkin
[17 empty] | Today's Date: |  |  |  |  | 2018-12-05
Project Status Update | [16 empty] | Overall Project Status: |  |  |  |  | At Risk
Category |  |  | Status |  | Project Manager's Notes
Action Items |  |  | On Track
Schedule |  |  | At Risk |  | Stakeholder outreach and development and review of member outreach understaffed
Risks |  |  | Off Track |  | RI NEMT contracts with MTM held up due to TP demands - 30% are contracted
Issues |  |  | On Track
Misc. |  |  | On Track
Anticipated vs. Actual Rate of Completion as of Today (Overall % and Task Count)
Start Date: |  |  | 2018-08-01 |  |  |  | Goal Completion Date: |  |  |  | 2018-12-31 |  |  |  | # Days until Goal Completion Date: | [8 empty] | 26
Risks | [5 empty] | Issues | [6 empty] | Questions | [6 empty] | Decisions
Unresolved |  |  | Resolved |  |  | Unresolved |  |  |  | Resolved |  |  | Unresolved |  |  | Resolved |  |  |  | Unresolved |  |  |  | Resolved
1 |  |  | 2 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 1 |  |  |  | 0 |  |  |  | 1
Action Items
Total |  | Complete |  | Critical |  |  |  | In Progress |  | Overdue |  | With Vendor |  | Blocked |  |  | Incomplete |  |  | Not Yet Due |  |  | Unknown
134 |  | 89 |  | 3 |  |  |  | 15 |  | 0 |  | 6 |  | 0 |  |  | 0 |  |  | 13 |  |  | 8
# | Objectives & Deliverables | [17 empty] | O / D | # Related Tasks |  |  |  | Tasks Complete
[24 empty] | # | %
1 | Systems implementation and data transfers (LogistiCare, MTM and EOHHS) | [17 empty] | D | 12 |  |  |  | 4 | 33.33%
2 | Transportation network adequacy and access | [17 empty] | O | 12 |  |  |  | 8 | 66.67%
3 | Policies and Procedures, Requirements, Compliance and Reporting | [17 empty] | D | 31 |  |  |  | 29 | 93.55%
4 | Stakeholder Engagement/Communications | [17 empty] | D | 31 |  |  |  | 10 | 32.26%
5 | Broker requirements | [17 empty] | O | 22 |  |  |  | 22 | 100%
6 | Operations | [17 empty] | D | 19 |  |  |  | 11 | 57.89%
7 | EOHHS Financial | [17 empty] | O | 5 |  |  |  | 4 | 80%
8 | Regulations and Policy | [17 empty] | D | 2 |  |  |  | 1 | 50%
Role | [8 empty] | Project Member Name | [8 empty] | Agency |  |  | Decision Rights
EOHHS Deputy Director | [8 empty] | January Angeles | [8 empty] | EOHHS |  |  | Approval Required
Project Lead | [8 empty] | Kristin Sousa | [8 empty] | EOHHS |  |  | Approval Required
Stakeholder Engagement/Systems | [8 empty] | Marlanea Peabody | [8 empty] | EOHHS |  |  | Consulted
Project Manager | [8 empty] | Maria Narishkin | [8 empty] | EOHHS
Transportation Team Lead | [8 empty] | Jason Lyon | [8 empty] | EOHHS
Transportation Team Manager | [8 empty] | Mario Olivieri | [8 empty] | EOHHS
Stakeholder Engagement | [8 empty] | Brenna McCabe and Diana Beaton | [8 empty] | EOHHS
Policy and Compliance | [8 empty] | Meghan Ruane and Ave Houston | [8 empty] | EOHHS
Impact Goal:
Implementation of new vendor contract including readiness and operations for the Medicaid non-emergency Medical Transportation program, the Elderly Transportation Program and transportation for TANF recipients
Opportunity Statement:
Anticipated Risks & Obstacles | [12 empty] | Key Performance Indicators
1 | LGTC not cooperating with transition -LGTC shared documents and transitioned toll free number | [11 empty] | 1
2 | [12 empty] | 2
3 | [12 empty] | 3
4 | [12 empty] | 4
Note on I6: If On Track, What are the most critical action items coming up? If Off Track, what are the the most critical action items to get back on track? If At Risk, what action items must be completed?
Note on I7: Is the project on schedule to hit its targets? If the goal of the "project" is to reach an outcome goal, are the metrics on track? If the project has a defined end point, have action items been completed in a timely manner?
Note on I8: What problems to achieving the project end or metrics may be encountered? What should the project lead focus on mitigating and how should it be done?
Note on I9: What challenges is the project currently facing? How should they be overcome?
Note on I10: What else should the project lead know about progress?
Note on A11: If the project manager is using the action item tab, this graph will automatically update to show actual project progress vs. anticipated project progress.
Note on A14: If the project manager is using the "Risks & Issues" tab, this will automatically update to show resolved and unresolved risks
Note on Q14: If the project manager is using the "Risks & Issues" tab, this will automatically update to show resolved and unresolved issues
Note on AG14: If the project manager is using the "Questions & Decisions" tab, this will automatically update to show resolved and unresolved questions
Note on AW14: If the project manager is using the "Questions & Decisions" tab, this will automatically update to show resolved and unresolved decisions
Note on C20: This part of the project charter should be used to highlight the work that needs to be performed by the team. For example, it could be gathering data and preparing an anlaysis, develoing and evaluation strategy, submitting a budget article. What written work or other concrete deliverable will the project accomplish?
Note on AT20: Objective or Deliverable
Note on AW20: If you are using the "Action Items" tab, include the corresponding objective or deliverable # in each action item, and this section will automatically update.
Note on A30: For each person on the project, why are they on the project? What contribution are they expected to make?
Note on BA30: Who is empowered to make decisions for the project? Who has the power to say yes?
Note on A39: What is the project trying to achieve? When this goal is achieved, the proejct will be closed (e.g. Launch website, reduce backlog to 10% of total applications, win $1m in grant funding)
Note on A41: Why is this project worth undertaking? What opporutnity does the group have to seize?
Note on A43: What does the group see as likely challenges that should be mitigated from the beginning of the project?
Note on AG43: What metrics will the project collect to know if it is being successful? At least some should be collected weekly to know that short term actions are having intended effects.

## Additional PM Notes
Please use this space to report qualitiative updates.
Progress:
Data from LGTC - going to stakeholder, discuss with stakeholders to have stakeholders discuss with logisticare. Can we get some information from TPs Open medical necessity for 6 months - no check needed List of all providers from DXC - Marlanea will send email Past 3 month history extract - to be used for volume for adequate network and to prepopulate Toll free numbers - Slide with a missing phone number. New phone number effective 12/18. Get a number by next week. Transition language in amendment. Get encounter data Get phone number - quick turn around, we can wait until next week. Communication about phone number by the end of November (stakeholder) Get info from facilities Meeting being set up with RIPTA for RIPTA bus pass plan (Wednesday) Ombudsman request - 1st quarter January ok with that
New Issues or Stalled Action Items:
Have there been meetings or communication with MTM's Reveal Team?
Cross-Agency Impact:
[Test text]
Escalations Suggested:
[Test text]

## Action Items
# | Action Item | Reason | Del | Accountable | Support | Origin | Created | Start | Due | Done | Status | Notes | . | Type of document/ proof of compliance | Document Name | Date Due to EOHHS | Date Provided by MTM | Date Reviewed By EOHHS | Reviewed By | Approved? | Date Sent back to MTM | Date Updated Document Received | Date Reviewed | Reviewed By | Approved ? | Notes
1.03 | Test enrollment file transfer for Medicaid Eligibility (834) | Eligibility | 1 | Marlanea | Steve DXC |  | 2018-09-26 | 2018-12-01 | 2018-12-05 | 2018-11-25 | Complete | 11/16 DXC check to see if it was received and MTM will send a list of questions by end of day. Second test file to go our 12/6 |  | Written Attestation |  | 2018-12-01
1.04 | Test enrollment file transfer for TANF Eligibility | Eligibility | 1 | Marlanea | Steve DXC - Steve Fugate |  | 2018-09-26 | 2018-12-01 | 2018-12-05 | 2018-11-25 | Complete | MTM is setting up a SFTP site for file transfers Steve is communicating with MTM re: questions on TANF files |  | Written Attestation |  | 2018-12-01
1.12 | Set up weekly meeting with EOHHS and LGTC |  | 1 | Jason | Mario |  |  | 2018-11-19 | 2018-11-21 | 2018-11-21 | Complete | Jason to contact LGTC for scheduling, invite sent for Wednesdays at 3:00PM
1.2 | Decide on MTM's request for post trip verification to be done through EOHHS and Medicaid medical claims | Post trip verification | 1 | Marlanea | January Kristin | Ops Meeting | 2018-11-20 | 2019-04-01 | 2019-04-30 | 2018-11-26 | Complete | Marlanea tabled this until after readiness - 90 post go live
2.03 | Approve TP contract template |  | 2 | Jason | Mario |  | 2018-09-26 |  | 2018-11-01 | 2018-11-20 | Complete | DPUC Standards must be in contract |  | Contract |  | 2018-11-01 |  |  |  | Yes
2.04 | Monitor number and types of TP contracts executed | Network adequacy | 2 | Jason | Mario Ave |  | 2018-09-26 | 2018-11-29 | 2018-11-29 | 2018-11-29 | Complete | * Requires weekly updates 11/20 EOHHS requested copy of signed contracts |  | Contracts |  | Weekly Updates
2.06 | Monitor and review GEO access map form MTM | Network adequacy | 2 | Jason | Mario |  | 2018-11-09 | 2018-11-29 | 2018-11-29 | 2018-11-29 | Complete | * Requires weekly updates |  | GeoAccess Map |  | Weekly Updates
2.07 | Provide current usage member data from LGTC to MTM | TP Network | 2 | Marlanea | Steve DXC |  | 2018-09-26 |  | 2018-11-16 | 2018-11-30 | Complete | LGTC has SFTP site to use for file transfers. 11/27 MTM did not respond to Jason's email inquiry, Jason forwarded to Genevieve EOHHS/LGTC Meeting scheduled for 11/28 11/29 meeting at 11:00am with Joe - Data expected by COB Friday 11/30 11/30 Data received from LGTC, reviewed by Steve, need Marlanea to review as well
2.08 | Provide encounter Data to MTM | MTM to use for provider recruitment effort | 2 | Marlanea | Steve DXC |  | 2018-09-26 |  | 2018-11-16 | 2018-11-20 | Complete | DXC is preparing data 11/16 5 encounter files were sent to DXC with member information
2.09 | ADA Eligibility RIPTA database sharing | Eligibility Verification | 2 | Marlanea | Steve DXC |  | 2018-09-26 |  | 2018-11-30 | 2018-11-27 | Complete | Not required
2.1 | Get list of all medical providers from DXC | To provide data to MTM | 2 | Marlanea | Steve DXC Jason |  | 2018-11-09 | 2018-11-14 | 2018-11-16 | 2018-11-27 | Complete | 11/19 Jason sent some contact files 11/21 Jason sent follow up email to DXC 11/26 DXC to send file 11/27 file review by Marlanea to be sent to MTM upon approval 11/28 Jason to send cleaned up list to MTM today
2.11 | Approve continuity of care for mode of transportation plan |  | 2 | Jason | Mario |  |  | 2018-11-15 | 2018-11-30 | 2018-11-29 | Complete | 11/27 MTM proposes 30 day period 11/28 Mario to forward to Brenna 11/29 Stacy confirmed 90 day CoC time from 1/1/19
3.01 | Staffing P&P Review | Contract Compliance | 3 | Jason | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-20 | Complete | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P | Compliance plan | 2018-11-01 |  |  |  | Yes | [5 empty] | Provided 2018 Compliance Plan
3.03 | Review FWA policy |  | 3 | Tom Bouchard | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-01 | 2018-11-20 | Complete | Received FWA plan, EOHHS Approved Meghan sent a list of P&Ps referenced in the FWA integrity plan 11/20 List sent to MTM |  | P&P | FWA Integrity Plan | 2018-11-21 |  |  | Tom Bouchard | Yes
3.05 | Review forms for Pre-trip verification |  | 3 | Jason | Ave Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-20 | Complete | Received pre-trip inspection report, vehicle inspection report and guidelines - EOHHS Approved |  | P&P | Daily pre-trip inspection report | 2018-11-01 |  |  |  | Yes
3.06 | Review forms for post-trip verification |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2019-04-01 | 2018-11-27 | Complete | Not due - grace period granted |  | P&P |  | 2018-11-21
3.13 | Review and approve P&P for TP monitoring, corrective action, termination… |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-23 | Complete | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.15 | Review and approve P&P for TP credentialing including background checks, review of CMS's List of Excluded Individuals and the System for Award Management |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-23 | Complete | Added requirements in action item at left 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.17 | Review and approve staff training curriculum |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-23 | Complete | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.18 | Review and approve Complaint resolution policy |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-23 | Complete | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P |  | 2018-11-21
3.22 | Review and approve TP manual |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-20 | Complete | 10/30/2018 Requesting extension on the delivery of this Manual – SB- MTM |  | P&P | RI Provider Handbook | 2018-11-21 |  |  | Meghan | Yes
3.27 | Review TP permits, licenses, insurance |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-05 | 2018-11-20 | Complete |  |  | Written Attestation | TP Appendix B | 2018-11-15 | 2018-11-12
3.28 | Review and approve P&P for TP vehicle compliance including PUC license, ADA compliance and vehicle inspection process and forms |  | 3 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-12-07 | 2018-11-20 | Complete | Received vehicle inspection guidelines and inspection form |  | P&P | Vehicle Inspection and guidelines, RI vehicle inspection form | 2018-11-01 |  |  |  | Yes | [5 empty] | Must still approve vehicle inspection form
3.32 | Review and approve Quality Assurance Policy |  | 3 |  | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-05 | 2018-11-20 | Complete | Received Policy, EOHHS Approved |  | P&P | 2018 Quality Assurance Program | 2018-12-01 |  |  |  | Yes
3.33 | Verify CCRs' multilingual capacity |  | 3 |  | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete | Received language attestation doc |  | Written Attestation | Language Attestation | 2018-12-15 |  |  |  | Yes
3.35 | Ensure compliance on AVL Capacity for vehicles (Written Attestation) |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2019-04-01 | 2019-04-08 | 2018-11-26 | Complete | EOHHS granted 90 day grace period from start of contract |  | Written Attestation |  | 2019-04-01
3.37 | Review and approve broker marketing materials | Marketing material review | 3 | Brenna | Diana |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-28 | Complete | Received RI postcard and Website text 11/18 Maria requests completion by COB 11/19 11/20 January requests that Meghan/Ave review and approve 11/27 Postcard text to include TANF and ETP info |  | RI Postcard and RI Website text | RI Postcard Text, RI Website Text | 2018-11-01 |  |  | Brenna, Diana Meghan and Ave
3.38 | Review and approve written material | Marketing material review | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-21 | Complete | Received RI ACA Language insert 11/16 Sent back to MTM with edits |  | As Documented | RI ACA Language Insert | 2018-11-01 |  |  |  | No | 2018-11-16
3.41 | Review TANF Rules |  | 3 | Mario |  |  |  | 2018-11-19 | 2018-11-21 | 2018-11-30 | Complete | Mario to look into TANF Policy and rules for bus pass distribution to member or entire household. 11/21 Mario to follow up 11/27 January to escalate
3.5 | Review/approve bus letter |  | 3 | Meghan | Ave |  |  | 2018-11-18 | 2018-11-22 | 2018-11-20 | Complete |  |  |  | Bus Letter |  | 2018-11-19 | 2018-11-19 | Meghan | No | 2018-11-19 | 2018-11-19 | 2018-11-20 | Meghan | Yes
3.51 | Review/approve Audit recoupment letter |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete |  |  |  | Audit Recoupment Letter |  |  |  |  | Yes
3.52 | Review/approve disaster recovery plan |  | 3 | Meghan | Ave |  |  | 2018-11-15 | 2018-11-21 | 2018-11-19 | Complete |  |  |  | Disaster Recovery |  | 2018-11-19 | 2018-11-19 | Ave | Yes | [5 empty] | Sent in lieu of staffing plan
3.53 | Review/approve GMR Trip log |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete |  |  |  | GMR Trip Log doc |  |  |  |  | Yes
3.54 | Review/approve incident/accident report form |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete |  |  |  | Incident/Accident Report form |  |  |  |  | Yes
3.54 | Review/approve LON Ambulance |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete |  |  |  | Level of Need - Ambulance |  |  |  |  | Yes
3.55 | Review/approve LON Standard |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete |  |  |  | Level of Need - Standard |  |  |  |  | Yes
3.56 | Review/approve MTM Currency Welcome Letter no public transit GMR Letter |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete |  |  |  | MTM Currency Welcome Letter - no public transit (GMR Letter) |  | 2018-11-19 | 2018-11-19 | Meghan | No | 2018-11-19 | 2018-11-19 | 2018-11-20 | Meghan | Yes
3.57 | Review/approve MTM Incoming call guide |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete |  |  |  | MTM Incoming call guide |  |  |  |  | Yes
3.58 | Review/approve MTM Provider Audit |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete |  |  |  | MTM Provider Audit |  |  |  |  | Yes
3.59 | Review/approve TP Helpdesk |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-21 | Complete |  |  |  | TP Helpdesk |  | 2018-11-12
3.6 | Review/approve Generic RFI |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete |  |  |  | Generic RFI |  |  |  |  | Yes
4.03 | Dialysis Meeting | MTM Meet & Greet | 4 | Mario |  |  | 2018-11-09 | 2018-11-07 | 2018-11-07 | 2018-11-07 | Complete
4.04 | Consumer Advisory Committee Meeting | Transition Update | 4 | Marlanea, January, Lissa, Diana |  |  | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | Complete
4.05 | Long Term Care Coordinating Council (LTCCC) Meeting | Transition Update | 4 | Marlanea, Mario, Mike |  |  | 2018-11-09 |  | 2018-11-14 | 2018-11-14 | Complete
4.06 | Substance Use and Leadership Council Meeting | MTM Meet-and-Greet/Overview | 4 | Marlanea, Jason, Mike, Kristin |  |  | 2018-11-09 |  | 2018-11-15 | 2018-11-15 | Complete | 9-10:30 am
4.08 | Stakeholder/Advocate Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-11-30 | 2018-11-30 | Complete | DXC/Confirmed
4.11 | Internal email to EOHHS, BHDDH, DEA, DHS staff meeting | Transition overview | 4 | Brenna |  |  | 2018-11-09 | 2018-11-09 | 2018-11-27 | 2018-12-03 | Complete | Signed by Patrick 11/20 Maria sent follow up email to Diana for update, moved to 11/27 11/30 Brenna sent final draft, edits sent back re: continuity of care 12/3 Patrick approved Memo, Brenna to send out to agencies.
4.13 | Adult Day Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 | 2018-11-29 | 2018-11-29 | 2018-11-29 | Complete | DXC
4.14 | EOHHS Task Force Meeting | Update, if asked | 4 | Brenna |  |  | 2018-11-09 |  | 2018-11-26 | 2018-11-26 | Complete | Confirmed, 11/26 cancelled
4.18 | Nursing Homes Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 | 2018-12-05 | 2018-12-05 | 2018-12-05 | Complete | DXC/Confirmed
4.3 | SUMHLC Provider meeting | Outreach | 4 | Jason | Brenna Diana |  | 2018-11-20 | 2018-12-03 | 2018-12-03 | 2018-12-03 | Complete | 9-10:30 SUMHLC - Confirmed
5.01 | Receive Performance Bond |  | 5 | Purchasing | Mario |  | 2018-09-26 | 2018-08-16 | 2018-08-16 | 2018-11-20 | Complete | Submitted with proposal |  | Certification |  | 2018-12-01 |  |  |  | Yes
5.02 | Receive Broker Professional Liability Insurance |  | 5 | Purchasing | Mario |  | 2018-09-26 | 2018-08-16 | 2018-08-16 | 2018-11-20 | Complete | Submitted with proposal |  | Certification |  | 2018-12-01 |  |  |  | Yes
5.03 | Receive Broker Workers' Compensation insurance |  | 5 | Purchasing | Mario |  | 2018-09-26 | 2018-08-16 | 2018-08-16 | 2018-11-20 | Complete | Submitted with proposal |  | Certification |  | 2018-12-01 |  |  |  | Yes
5.04 | Receive Broker automobile Liability |  | 5 | Purchasing | Mario |  | 2018-09-26 | 2018-08-16 | 2018-08-16 | 2018-11-20 | Complete | Submitted with proposal |  | Certification |  | 2018-12-01 |  |  |  | Yes
5.05 | Staffing Implementation Plan |  | 5 |  |  |  | 2018-09-26 | 2018-09-30 | 2018-10-15 | 2018-09-30 | Complete | Received |  | Written Attestation | Staffing plan | 2018-11-01 | 2018-09-25 |  |  | Yes | [5 empty] | Submitted with Contract
5.06 | Identify office location | Ensure the location complies with contract requirements | 5 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-01 | 2018-11-20 | Complete | Received trade name certificate Do we have copy of lease? 11/28 MTM Provided Lease |  | Lease |  | 2018-11-01 |  |  |  | Yes
5.07 | Ensure broker is licensed in RI | Contract Compliance | 5 | Jason | Mario |  | 2018-09-01 | 2018-11-01 | 2018-11-01 | 2018-11-20 | Complete | Received MTM RI Cert of good standing |  | License | MTM RI Cert of Good Standing | 2018-11-01 |  |  |  | Yes
5.08 | Ensure broker is registered as a state vendor | Contract Compliance | 5 | Jason | Mario |  | 2018-09-01 | 2018-11-01 | 2018-11-01 | 2018-11-20 | Complete | Received MTM RI Enrollment Status |  | Registration / Written Attestation | MTM RI Enrollment Status | 2018-11-01 |  |  |  | Yes
5.09 | Review and approve key management positions to be located in RI | Contract Compliance | 5 | Jason | Mario |  | 2018-08-09 | 2018-09-30 | 2018-11-01 | 2018-09-30 | Complete | Staffing plan submitted with contract |  | Written Attestation | Staffing plan | 2018-11-01 | 2018-09-25 |  |  | Yes | [5 empty] | Submitted with Contract
5.11 | Ensure RI operation is fully staffed (written attestation) | Contract Compliance | 5 | Jason | Ave Meghan |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-25 | Complete | Concern with CCRs working from home. 10/30/18 MTM CCR staff will be located onsite at RI office. 1st training class slated for 11/12/18 Concern with HIPAA and privacy for remote people. Need clear policies. |  | Written Attestation |  | 2018-12-01
5.12 | Receive Broker certification of truthfulness |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete |  |  | Certification | Warranties section of contract | 2018-12-01 |  | Jason |  | Yes | [5 empty] | 11.12.18: sent clarification 11.9.18 on the intent of this certification. Based on MTM legal review, MTM attested to this by signing the contract.
5.13 | Receive Broker certification of Legality |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete |  |  | Certification | Warranties section of contract | 2018-12-01 |  | Jason |  | Yes | [5 empty] | 11.12.18: sent clarification 11.9.18 on the intent of this certification. Based on MTM legal review, MTM attested to this by signing the contract.
5.14 | Receive Broker insurance endorsement |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete |  |  | Certification | MTM Certificates of insurance | 2018-12-01 |  |  | Jason | Yes | [5 empty] | 11.12.18: sent clarification 11.9.18 on the intent of this certification. Based on MTM legal review, MTM attested to this by signing the contract.
5.15 | Receive Broker Comprehensive Liability Insurance |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete |  |  | Certification | MTM Certificates of insurance | 2018-12-01 |  | Jason |  | Yes | [5 empty] | 11.12.18: sent clarification 11.9.18 on the intent of this certification. Based on MTM legal review, MTM attested to this by signing the contract.
5.16 | Receive Broker Property Damage Insurance |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete |  |  | Certification | MTM Certificates of insurance | 2018-12-01 |  | Jason |  | Yes | [5 empty] | 11.12.18: sent clarification 11.9.18 on the intent of this certification. Based on MTM legal review, MTM attested to this by signing the contract.
5.17 | Receive Broker Errors and Omissions insurance |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete |  |  | Certification | MTM Certificates of insurance | 2018-12-01 |  | Jason |  | Yes | [5 empty] | 11.12.18: sent clarification 11.9.18 on the intent of this certification. Based on MTM legal review, MTM attested to this by signing the contract.
5.18 | Ensure Broker's ability to maintain confidential information (written attestation) |  | 5 | Jason | Ave |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-26 | Complete |  |  | Written Attestation |  | 2018-12-01
5.19 | Broker's disclosure of ownership and control interest |  | 5 | Jason | Ave Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete |  |  | Written Attestation | RI Disclosure of Ownership | 2018-12-01 |  |  |  | Yes
5.22 | Broker's Ombudsman to be located in Rhode Island by end of 2019 Q1 | Staffing | 5 | Jason | Ave Mario |  | 2018-11-09 | 2018-11-09 | 2019-03-31 | 2018-11-28 | Complete | State approved broker's ombudsman to be located in RI by end of 2019 Q1 |  | Ombudsman hired 12/3/18 start date
5.23 | MTM to consider employing from RI Works, RI Unemployment, M/WBE (P&P) | Staffing | 5 | Jason | Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-20 | Complete | Lissa to touch base with Kim Rauch. MTM MTM asking for clarification on unemployment, MTM requested extension for delivery of this manual, approved by EOHHS 10/30/18 |  | P&P | RI Works Contracts and Recruiting Info | 2018-11-01 | 2018-11-16 | [8 empty] | Still need Unemployment/M/WBE
5.24 | Ensure Broker's ability to maintain records for 10 years (written attestation) |  | 5 | Jason | Ave |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-26 | Complete |  |  | Written Attestation |  | 2018-12-01
5.26 | Review and approve Implementation Plan | Operations/transition | 5 | Jason | Mario |  | 2018-09-26 | 2018-10-15 | 2018-11-01 | 2018-01-20 | Complete | Received implementation plan (MTM Project Plan) |  | Written Attestation | RI NEMT Implementation | 2018-10-15 | 2018-09-01 |  |  | yes
6.01 | EOHHS Meeting with RIPTA | Bus Pass technology | 6 | Jason | January Kristin |  | 2018-11-08 |  | 2018-11-14 | 2018-11-20 | Complete
6.03 | Transfer of toll-free number(s) from LGTC to MTM or acquire new numbers | Operations | 6 | Marlanea | Jason |  | 2018-09-26 | 2018-11-16 | 2018-11-21 | 2018-11-27 | Complete | Marlanea to confirm acquisition of new toll free number with MTM by 11/14 11/19 LGTC/MTM/EOHHS conference call. LGTC will transfer main reservation number to MTM. Number to port on 12/17 at 6PM. LGTC to send port form by 11/20 and will get temporary number for 12/18-12/31. LGTC will send language for approval for post 1/1 11/21 LGTC sent number transfer documents to MTM |  | Written Attestation |  | 2018-12-15
6.05 | Ensure availability of Telephone Device for the Deaf (TDD) | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-15 | 2018-12-18 | 2018-11-27 | Complete | 11/19 MTM Stated that they use global 711 for this service. Kristin is ok with this but this information needs to be advertised |  | Written Attestation |  | 2018-12-15
6.08 | EOHHS to provide contact information and ensure connection between MTM and MCOs for coordination of services with MCOs | Stakeholder engagement | 6 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-20 | Complete | Provided in outreach plan - MCOs are not specifically mentioned in the outreach plan but MTM includes MCOs as part of their outreach plan when directed by client |  | Written Attestation | Same as 4.01 plus: VOC Presentation | 2018-11-01 | [9 empty] | Provided in outreach plan
6.09 | EOHHS to provide contact information and ensure connection between MTM and AEs for coordination of services with Coordination of services with AEs | Stakeholder engagement | 6 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-27 | Complete | Provided in Outreach Plan - Identify Key Stakeholders (Advocacy Groups/Legislators/NEMT Advisory Committee), Federally Recognized Tribes, Refugee Populations, Health Care Providers, Provider Associations, Community Base Organizations, Consumer Representatives Discuss with EOHHS any special needs groups – MTM 11/20 Maria emailed Diana to add AEs to stakeholder list |  | Written Attestation |  | 2018-11-01
6.1 | EOHHS to provide contact information and ensure connection between MTM and RIPTA for coordination of services with RIPTA's RIde Program | Stakeholder engagement | 6 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-20 | Complete | Establish contact and open communication with public transit entities/ADA para-transit providers, escalate information to Network Management Community Outreach collaborates with Logistics to provide necessary information regarding fixed route and ADA information. - MTM |  |  |  | 2018-11-01
6.1 | RIPTA and MTM Meeting | Bus Pass distribution | 6 | Jason | Mario |  |  | 2018-11-21 | 2018-11-28 | 2018-11-28 | Complete | Bus pass distribution, Jason is setting up meeting Scheduled (11/28 12:00pm)
6.11 | EOHHS to provide contact information and ensure connection between MTM and high-utilizing providers for coordination of services with high-utilizing providers (Adult day, Dialysis, SUD, etc.) | Stakeholder engagement | 6 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-28 | Complete | Need data from DXC 11/28 Jason sent data to MTM |  |  |  | 2018-11-01
6.15 | Finalize bus pass distribution process |  | 6 | Jason | Mario |  |  | 2018-11-15 | 2018-11-28 | 2018-11-29 | Complete | Discuss during RIPTA meeting 11/28
6.18 | Approve LGTC phone recording for 1/1 |  | 6 | Jason |  |  | 2018-11-20 |  | 2018-11-30 | 2018-11-30 | Complete
6.2 | Respond to request for grace period for post-trip verification requirements | Broker Requirements | 6 | Jason | Kristin | Ops Meeting | 2018-11-20 | 2018-11-21 | 2018-11-21 | 2018-11-26 | Complete | 11/26 Jason to email MTM on approval of grace period
7.01 | Ensure pathway for assessing liquidated damages to Broker | Finance | 7 | Mario | Kathy Corsino |  | 2018-09-26 |  | 2018-12-01 | 2018-11-30 | Complete | EOHHS granted 180 day grace period from start of contract 11/27 Mario to confirm with DXC/Fiscal that MTM would issue a check to EOHHS
7.02 | Ensure pathway to send capitation payments for Medicaid members to MTM | Finance | 7 | Marlanea | Kathy Corsino |  | 2018-09-26 |  | 2018-12-01 | 2018-11-27 | Complete | Bank info, ACH info complete
7.03 | Ensure pathway to send payments for the ETP program | Finance | 7 | Mario | Kathy Corsino |  | 2018-09-26 |  | 2018-12-01 | 2018-12-04 | Complete | 11/27 Mario sent email to DHS CFO re issue with budget account 12/3 Waiting for Purchases approval
7.04 | Ensure pathway to send payments for TANF program | Finance | 7 | Mario | Kathy Corsino |  | 2018-09-26 |  | 2018-12-01 | 2018-12-04 | Complete | 11/27 Mario sent email to DHS CFO re issue with budget account 12/3 Waiting for Purchases approval
8.02 | CMS Approval of Transportation SPA | State Plan | 8 | Melody Lawrence | Mario |  | 2018-09-26 |  | 2018-12-31 | 2018-12-04 | Complete | 11/19 Maria emailed Mel for update, CMS is waiting for final pages and will send the approval letter. 11/27 CMS unofficially approved, waiting for approval letter
2.05 | Monitor and ensure TP supply adequacy | Operations | 2 | Jason | Mario |  | 2018-09-26 | 2018-11-29 | 2018-11-29 |  | Critical | 12/4 MTM, RI NEMT and EOHHS met to discuss and will reconvene 12/5 with option of MOU to satisfy both parties |  |  |  | Weekly Written Updates
4.01 | Send approved postcard to Medicaid, ETP and TANF members | Stakeholder engagement | 4 | Brenna | Diana Jason Meghan Ave |  | 2018-09-26 | 2018-11-01 | 2018-11-07 |  | Critical | 12/3 Postcard approved, MTM to print and send to all members + ETP + TANF 12/4 Member file from DXC needed |  | Comm and education plan: Website text, postcard text, town hall sign in, PPT… | Comm & Education Plan, Facility Implementation, Town Hall sign-in, Facility intro letter, MTM Overview presentation, State Resource guide |  |  |  |  | No Comm/ed plan with Comm team | 2018-11-16 |  |  |  |  | 11/19 Jason sent comments to MTM on Presentation
4.5 | Draft and send targeted member letter to exiting users in Medicaid and ETP Programs | Communication | 4 | Brenna | Diana Meghan/Ave Legal |  | 2018-12-03 | 2018-12-03 | 2018-12-07 |  | Critical | 12/3 Brenna to draft letter and send to team for review by COB 12/4 12/4 Letter to be reviewed by Meghan/Ave and Legal, Mail room to be notified, Michelle to expedite translations and do mail merge. Letter to be sent out by COB 12/7
1.06 | Update TANF eligibility files to include dependent information |  | 1 | Marlanea | Steve Bridges/ Deloite |  |  | 2018-12-20 | 2019-01-15 |  | In Progress | 12/5 January confirmed with DXc that the TANF files sent to the broker includes all members of the household. EOHHS to inform MTM and clarify that members under the age of 5 do not need a bus pass. | [14 empty] | 11/28 Steve following up with Nicole to get an ETA, currently not prioritized with Bridges, January emailed Nicole to prioritize request
1.14 | Review MTM's TP Claims processing function |  | 1 | Steve |  |  | 2018-09-26 |  | 2018-12-10 |  | In Progress | 12/4 Steve to contact MTM for test run and results | [14 empty] | Mario to email Kim Rauch to get member and household members file by 12/4
2.12 | Chart TP supply in comparison with LGTC | TP Network | 2 | Mark | Mario |  | 2018-11-30 | 2018-11-30 | 2018-12-15 |  | In Progress | 12/3 Focus on ambulance 30% of TP supply contracted
2.3 | Review MTM's list of providers from which they acquired standing order information | Standing orders | 2 | Jason | Mario | Ops Meeting | 2018-11-20 | 2018-11-29 | 2018-12-12 |  | In Progress | MTM to provide weekly updates starting next ops meeting on 11/29 11/28 MTM Provided list of facilities they outreached to, 2 provided standing order lists 11/29 Marlanea requests information on other types of providers, not just Dialysis and Adult Day
3.02 | Review and approve RI Operating Procedure Manual |  | 3 | Meghan Jason | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-12-05 |  | In Progress | 11/30 Ave sent her edits to Jason, Meghan will send hers w/e 12/7. Items marked for Jason and Mario to review. 12/4 about 95% complete |  | P&P |  | 2018-11-21
3.36 | Review proposed report templates and ensure they meet contract requirements |  | 3 | Mark | Mario Meghan |  | 2018-09-26 | 2018-11-21 | 2018-12-09 |  | In Progress | 11/27 Maria to forward templates to Mark, Ave, Meghan, Mario, January, Marlanea |  | P&P |  | 2018-11-21 | 2018-11-15
4.15 | Home Care Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-05 | 2018-12-05 | In Progress | 10-10:45 Warwick Library
4.24 | Managed Care Organizations & Dental Meeting | Update, as needed | 4 | January and Kristin |  |  | 2018-11-09 |  | 2018-11-27 |  | In Progress | As needed on Tuesdays' oversight meetings, have Mark put on agenda Schedule separate meeting
4.25 | MTM Town Hall Meeting | General Information (MTM) | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | In Progress | For TPs
6.02 | Review and approve MTM Website | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | In Progress | 12/4 - to be discussed at 4:00pm meeting with Marlanea and MTM
6.12 | Review and approve proposed vehicle placard |  | 6 | Jason | Mario Meghan |  | 2018-11-28 | 2018-11-28 | 2018-12-07 |  | In Progress | Discuss during meeting with MTM 11/28 12/3 Mario to set up a meeting with DPUC 12/4 DPUC stated that there can only magnetic EOHHS placards on PMVs
6.13 | Review and approve proposed driver ID badges |  | 6 | Jason | Mario Meghan |  | 2018-11-28 | 2018-11-28 | 2018-12-07 |  | In Progress | Discuss during meeting with MTM 11/28 12/3 Mario to set up a meeting with DPUC
6.16 | State participation in call overflow, RHO call center (provider outreach LON and Standing orders) |  | 6 | Marlanea | Mark Lani |  | 2018-11-30 | 2018-11-30 | 2018-12-07 |  | In Progress | Meeting set with Lani, Kristin, Marlanea, January and Mark to create a business flow 12/3 Re-schedule meeting with Meg Carpinelli - waiting for her to send new date and time
6.17 | Address provider questions (Adult Day) |  | 6 | Jason | Diana Maria |  | 2018-11-29 | 2018-11-30 | 2018-12-08 |  | In Progress | 11/30 Maria to combine all questions into one doc 11/30 Dana reviewed and emailed back
8.01 | Promulgation of Transportation Policy | State Policy | 8 | Tarah Provencal | Mario |  | 2018-09-26 | 2018-11-13 | 2018-12-31 |  | In Progress | 11/13 Mario and Jason to send answers to stakeholder questions to January for review 11/19 Updated complete tracked changes regs sent to January 11/20 January sent final answers to legal for approval, Lisa Marinelli approved, 11/21 Tarah sending to ORR. 11/27 Tarah sent to ORR on 11/26 and turn around time is up to 30 days. She will get update from them
1.01 | Send Medicaid Production File | Eligibility | 1 | Marlanea | Steve DXC |  |  | 2018-12-08 | 2018-12-08 |  | Not Yet Due | DXC to send files by 10:00PM 12/8
1.02 | Send TANF Production File | Eligibility | 1 | Marlanea | Steve DXC |  |  | 2018-12-08 | 2018-12-10 |  | Not Yet Due | DXC to send files 12/10 (evening)
1.07 | MTM to sent provider files to DXC |  | 1 | Marlanea | Steve DXC |  |  | 2019-01-15 | 2019-04-30 |  | Not Yet Due | Does MTM have a template for this? Not started, will complete after go-live in the spring
1.08 | Test and verify broker's ability for 837 Encounter data submission |  | 1 | Marlanea | Steve DXC |  | 2018-09-26 | 2019-04-01 | 2019-04-30 |  | Not Yet Due | Not started, will complete after go-live in the spring
1.09 | Send test Change file | Eligibility | 1 | Marlanea | Steve DXC |  |  | 2018-12-03 | 2018-12-14 |  | Not Yet Due
4.07 | Assisted Living Providers Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 | 2018-11-30 | 2018-12-07 |  | Not Yet Due
4.09 | Stakeholder/Advocate Meeting | Transition update | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-20 |  | Not Yet Due | 9-10 DXC - invite needs to be sent out]
4.17 | Senior Centers Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 | 2018-12-13 | 2018-12-13 |  | Not Yet Due | 12-1 DXC Pending
4.22 | Long-Term Care Coordinating Council (LTCCC) Meeting | Transition Update | 4 | Mario, Marlanea | Brenna Diana |  | 2018-11-09 |  | 2018-12-12 |  | Not Yet Due | Confirmed 10-11:30 am
4.23 | EOHHS Task Force Meeting | Transition Update | 4 | Marlanea | Brenna Diana |  | 2018-11-09 |  | 2018-12-17 |  | Not Yet Due | Confirmed 1-2:30 DXC
4.28 | Long-Term Care Coordinating Council (LTCCC) Meeting | Transition Update | 4 | Brenna | Diana |  | 2018-11-09 |  | 2019-01-09 |  | Not Yet Due | Confirmed, Child and Family in Providence
4.29 | EOHHS Task Force Meeting | Transition Update | 4 | Marlanea | Brenna Diana |  | 2018-11-09 |  | 2019-01-28 |  | Not Yet Due | DXC Confirmed, check to see if on agenda
4.31 | VA Meeting | Outreach | 4 | Mario | Diana |  | 2018-11-28 | 2018-12-10 | 2018-12-10 |  | Not Yet Due | Room 235 Mike Jolin
4.12 | Federally recognized tribes Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Unknown | TBD
4.16 | DEA Providers Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Unknown | TBD
4.19 | FQHCs Meeting | Transition update | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Unknown | TBD DEC
4.2 | Children’s Services Providers Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Unknown | TBD DEC
4.21 | Hospitals/HARI Meeting | MTM Meet-and-Greet/Overview | 4 | Mike C. | Brenna Diana |  | 2018-11-09 |  | 2018-12-15 |  | Unknown | TBD DEC
4.26 | Meeting with All Other Providers (Waiver Group)/Personal Choice/Care Mgmt |  | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Unknown | TBD
4.27 | DXC Listservs Meeting |  | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Unknown | TBD
4.32 | Resident Service Coordinators meeting | Outreach | 4 | Jason | Brenna Diana |  |  |  | 2018-12-15 |  | Unknown | TBD DEC
1.05 | Review P&P for retroactive eligibility claims processing |  | 1 | Marlanea | Steve Bridges |  | 2018-09-26 | 2018-12-01 | 2018-12-05 |  | With Vendor | Mario to email MTM fiscal re process |  | P&P |  | 2018-12-01
2.31 | Review determination on dialysis center transportation modes review by MTM | Dialysis transport | 2 | Mario | Jason | Ops Meeting | 2018-11-20 | 2018-11-29 | 2018-11-30 |  | With Vendor | Discuss during meeting with MTM 11/27 and 11/29
6.04 | Review and approve Mobile Apps (written attestation) | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | With Vendor |  |  | Written Attestation |  | 2018-12-01
6.06 | Ensure Automatic call distributor (ACD) is operational (written attestation) including call flow routing, call tracking and call extraction and reporting | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-15 | 2018-12-18 |  | With Vendor |  |  | P&P |  | 2018-12-15
6.07 | Verify that telephone backup system is operational (written attestation) | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-15 | 2018-12-18 |  | With Vendor |  |  | Written Attestation |  | 2018-12-15
7.05 | Approve MTM financial reporting policy and templates | Finance | 7 | Mario | Kathy Corsino |  | 2018-09-26 | 2019-02-01 | 2019-02-10 |  | With Vendor | 11/27 Mario sent email to MTM requesting sample of monthly financial statement and will provide to Kathy for approval. Also reaffirming requirement of yearly audited review |  | P&P |  | 2019-02-01

## Risks & Issues
# | Risk / Issue | Origin | Date Created | Date Due | Description | Mitigation Plan | Primary Owner | Status | Notes
1.01 | Risk | 11/9 Internal Meeting | 2018-11-09 | 2018-11-16 | LGTC not providing member files | Acquire information from encounter data and facilities, open medical necessity for 3 or 6 months | Marlanea | Resolved | Marlanea is lead in systems
1.02 | Risk |  | 2018-11-09 | 2018-11-20 | Transition of toll free number from LGTC | MTM to acquire new toll free number | Marlanea | Resolved
2.01 | Risk |  | 2018-11-30 |  | RI NEMT TPs - pushing back on contracting with MTM - can result in inadequate TP network | MTM suggests contracting with RIPTA 12/4 MTM/RI NEMT and EOHHS met and are followint up 12/5 re: possible MOU to satisfy both parties

## Questions & Decisions
# | Question / Decision | Origin | Date Created | Date Due | Description | Outcome | Primary Owner | Status | Notes
1 | Question | 11/8 MTM Meeting | 2018-11-08 | 2018-11-30 | 10% pre and post verification partnering with EOHHS - what is the timeline for post-trip verification - change the percentage | 90 post implementation review |  | Resolved | 10% would take 4 full-time positions, can we decrease the percentage or give encounter data to MTM to use for trip verification
4.01 | Decision |  |  | 2018-12-03 | Decision on mailing the postcard as is or amending. Do we want to create a separate mailing? | Create 2 separate mailings |  | Resolved

## Project Metrics (hidden)
Metric # | Metric | Definition | Data Source | Person Responsible | Target Value | Target Goal | Target Date | Frequency | 2018-09-16 | 2018-09-23 | 2018-09-30 | 2018-10-07 | 10/14/2018 | 10/21/2018 | 10/28/2018 | 11/4/2018
1 | # of Overdue Applications in State Hands | # of applications pending after receipt from client that are workable by the State for more than 90 days | RIB Tableau KPI | XYZ |  |  |  | Weekly

## Data Validation (hidden)
Status | Project Manager | AI Status | QRID Status | Frequency | Agency | Decision Rights | Anticipated vs. Actual Completed by Today's Date
On Track | Jasper Frank | Blocked | Blocked | Daily | BHDDH | Approval Required | Start Date: | 2018-08-01
At Risk | Catherine Gering | Complete | In Progress | Weekly | DCYF | Consulted | Today's Date: | 2018-12-05
Off Track | Matt Kiehnle | In Progress | Not Yet Due | Monthly | Deloitte | N/A | End Date: | 2018-12-31
Other | Maria Narishkin | Incomplete | Overdue | Quarterly | DHS |  |  | Anticipated | Actual
|  | Not Yet Due | Resolved |  | EOHHS |  | Complete | 79 | 89
|  | Overdue | Unknown |  | HSRI |  | Incomplete | 55 | 45
|  | Unknown | Unresolved |  | Medicaid |  |  | 58.96% | 66.42%
|  | With Vendor | With Vendor |  | Other
|  | Critical |  |  | RIDOH
|  | Total | Total
|  | Complete | Resolved |  |  |  | Total Tasks | 134
|  | In Progress | In Progress
|  | Not Yet Due | Not Yet Due
|  | Unknown | Unknown
|  | Blocked | Blocked
|  | Incomplete | Unresolved
|  | Overdue | Overdue
Risks
Issues
Questions
Decisions