## Document Review
Document Name | Date due to EOHHS | Date Provided by MTM | Date Reviewed By EOHHS | Reviewed By | Approved? | Date Sent back to MTM | Date Updated Document Received | Date Reviewed | Reviewed By | Approved ? | Notes
ACA Language Insert | 2018-11-01 |  |  | Jason | No | 2018-11-16 |  |  |  | Yes | They should be using the state template
Ambulance provider handbook |  | 2018-10-11 | 2018-10-26 | Mario and Jason | Yes
Audit Recoupment Letter |  |  |  | Jason and Mario | Yes
Authorization for transportation request form |  |  |  | Jason and Mario | Yes
Bus Letter |  | 2018-11-19 | 2018-11-19 | Meghan | No | 2018-11-19 | 2018-11-19 | 2018-11-20 | Meghan | Yes
CC urgent request guidelines |  |  |  | Jason and Mario | Yes
Communication and education plan
Complaint resolution letter |  |  | 2018-11-20 | Meghan | No | 2018-11-20
Compliance plan | 2018-11-01 |  |  | Jason and Mario | Yes | [5 empty] | Provided 2018 Compliance Plan
Daily pre-trip inspection report | 2018-11-01 |  |  | Jason and Mario | Yes
Disaster Recovery |  | 2018-11-19 | 2018-11-19 | Ave | Yes | [5 empty] | Sent in lieu of staffing plan
Distance verification form |  |  |  | Jason and Mario | Yes | 2018-11-20
Facility Implementation Spreadsheet |  |  |  | Jason and Mario | No |  | 2018-11-20 |  | Jason | Yes
Facility intro letter |  |  |  | Jason and Mario | No |  | 2018-11-20 |  | Jason | Yes
FWA Integrity Plan | 2018-11-21 |  |  | Tom Bouchard | Yes
Generic RFI |  |  |  | Jason and Mario | Yes
GMR Trip Log doc |  |  |  | Jason and Mario | Yes
Implementation | 2018-10-15 | 2018-09-01 |  | Jason and Mario | yes
Language Attestation | 2018-12-15 |  |  | Jason and Mario | Yes |  | 2018-11-30 | 2018-11-30 | meghan | Yes
Level of Need - Ambulance |  |  |  | Jason and Mario | Yes
Level of Need - Standard |  |  |  | Jason and Mario | Yes
Member behavior - action taken |  |  |  | Jason | No | 2018-11-16
Member behavior - education letter |  |  |  | Jason | No | 2018-11-16
Member behavior - warning letter |  |  |  | Jason | No | 2018-11-21
MTM Currency Welcome Letter - no public transit (GMR Letter) |  | 2018-11-19 | 2018-11-19 | Meghan | No | 2018-11-19 | 2018-11-19 | 2018-11-20 | Meghan | Yes
MTM Incoming call guide |  |  |  | Jason and Mario | Yes
MTM overview PP |  |  |  | Jason | No | 2018-11-16 | 2018-11-21 |  | Jason | Yes | Sent back to EOHHS again
MTM Protocols |  |  |  | Jason | Yes
MTM Provider Audit
No Show letter level 2 |  |  |  | Meghan/Jason | Yes
No show letter level 3 |  |  |  | Meghan | No | 2018-11-20
Policy 2001 New hire orientation |  | 2018-11-20 |  | Ave | Yes
Policy 413 Management of No Shows |  | 2018-11-28 |  | Meghan | no
Policy 435 Compliance and ethics |  | 2018-11-20 |  | Ave | Yes
Policy 437 Compliance and ethics education training/outreach |  | 2018-11-20 |  | Meghan | Yes
Policy 702 Annual compliance training |  | 2018-11-20 |  | Ave | Yes | [5 empty] | Submitted with Contract
Policy 753 Documentation of ongoing training |  | 2018-11-20 |  | Ave | Yes
Policy 9902 Regulatory Compliance |  | 2018-11-20 |  | Ave | Yes
Postcard Text | 2018-11-01 |  |  | Meghan | No | 2018-11-21 | 2018-11-29 | 2018-11-30 | Meghan | Yes
Procedue 602.007 Pre and post validation |  | 2018-11-20 |  | Ave | Yes
Procedure 606.001 Claims web application-verification of claims |  | 2018-11-20 |  | Ave | Yes
Procedure 700.002 sanction check search process |  | 2018-11-20 |  | Meghan | Yes
Provider Handbook | 2018-11-21 |  |  | Meghan | Yes
Quality Assurance Program | 12/1/2018 |  |  | Jason and Mario | Yes
REPORT - Accident/incident client report |  | 2018-11-02
REPORT - Claims timeliness report |  | 2018-11-02
REPORT - Contact Center report - Call Queue |  | 2018-11-02
REPORT - Contact Center report - Call stats |  | 2018-11-02
REPORT - Monthly client summary report |  |  |  | Meghan
REPORT - Monthly complaint report |  | 2018-11-02
REPORT - RI dashboard |  | 2018-11-02
REPORT - Sample Denial Detail Report |  | 2018-11-02
REPORT - Sample FWA report |  | 2018-11-02
REPORT - Sample Plan Detail Month Year |  | 2018-11-02
REPORT - Sample pre/post dashboard |  | 2018-11-02
REPORT - TP Monthly Report Card
REPORT - Trip detail report
RI Operating procedures manual | 2018-11-21 | 2018-11-20 | [8 empty] | See Ops Manual tab for checklist of P&Ps
RI Works document
Staffing plan | 2018-11-01 | 2018-09-25 |  | Contract review | Yes | [5 empty] | Submitted with Contract
State Denial Letter |  | 2018-11-09 |  | Meghan | No | [5 empty] | Edits sent to Jason
State resource guide |  | 2018-11-20 |  | Jason | No | 2018-11-21
Town hall sign-in |  |  |  | Comm. Team
TP Contract Appendix A
TP Contract Appendix B | 2018-11-15 | 2018-11-12 |  | Jason and Mario | Yes
TP Contract Appendix C
TP Contract Schedule A
TP Contract Schedule B
TP Contract TPSA
TP Helpdesk |  | 2018-11-12 |  | Jason and Mario | Yes
TP Training Ambulance community user credentialing reference guide |  | 2018-11-02 |  | Meghan | Yes
TP Training Ambulance provider reference guide |  | 2018-11-02 |  | Meghan | Yes
TP Training Appeals reference guide |  | 2018-11-02 |  | Meghan | Yes
TP Training Claims reference guide |  | 2018-11-02 |  | Meghan | Yes
TP Training Community User Credentialing PP |  | 2018-11-02 |  | Meghan | Yes
TP Training Community User Credentialing reference guide |  | 2018-11-02 |  | Meghan | Yes
TP Training Cultural Competency PP |  | 2018-11-02 |  | Ave | Yes | [5 empty] | Where are these docs, not detailed in Provider Handbook
TP Training Denial reasons Claims FAQ |  | 2018-11-02 |  | Meghan | Yes
TP Training ETD reference Guide |  | 2018-11-02 |  | Meghan | Yes
TP Training New provider Training and nesting | 2018-11-01 | 2018-10-30 |  | Meghan | Yes
TP Training Provider Trip management reference guide |  | 2018-11-02 |  | Meghan | Yes
TP Training PTM and ETP PP |  | 2018-11-02 |  | Meghan | Yes
TP Training Reveal driver app reference guide |  | 2018-11-02
TP Training Reveal driver app training PP |  | 2018-11-02
TP Training Reveal Provider portal PP |  | 2018-11-02
TP Training Reveal proviider portal reference guide |  | 2018-11-02
TP Training TP Compliance Training PP |  | 2018-11-02 | 2018-11-26 | Ave | [6 empty] | Where are these docs
Vehicle Inspection and guidelines | 2018-11-01 |  |  | Jason and Mario | Yes
Vehicle inspection form | 2018-11-01 |  |  | Jason and Mario | Yes
VOC Presentation | 2018-11-01 |  | 2018-11-19 | Jason and Mario | No | 2018-11-21 |  |  |  |  | Provided in outreach plan
Website Text |  |  | 2018-11-20 | Meghan | No | 2018-11-21

## Ops Manual
Policy or process | Date due to EOHHS | Date Provided by MTM | Date Reviewed By EOHHS | Reviewed By | Approved? | Date Sent back to MTM | Date Updated Document Received | Date Reviewed | Reviewed By | Approved ? | Notes
Accident/incident escalation process |  |  |  | X
Alternative transportation options
Ambulance Contracting
Attendent/escort policy
Authorizing and scheduling services
Breach of confidentiality process |  |  | 2018-11-26 | Ave | Yes
Bus Route entry
Bus Route fare inventory
Call center service disruption |  |  | 2018-11-23 | Meghan | Yes
Call monitoring/evaluation |  |  | 2018-11-23 | Meghan | yes
CCR response standards
Challenging member policy
Client audit management |  |  | 2018-11-23 | Meghan | Yes
Complaint resolution policy |  |  | 2018-11-23 | Meghan | Yes |  |  | 2018-11-23 | Meghan | yes
Compliance hotline |  |  | 2018-11-26 | Ave | No |  |  |  | Ave | No | Section #3, what is the significance of KPI as it relates to Hotline
Cust serv cntr interaction conduct |  |  | 2018-11-23 | Meghan | Yes
Denial of service letter |  |  | 2018-11-23 | Meghan | No |  |  | 2018-11-28 | Meghan | No
Document retention |  |  | 2018-11-26 | Ave | Yes
Eligibility verification process
Emergency situations |  |  |  | Meghan |  |  |  | 2018-12-05 | Meghan | Yes
Expedited resolutions of appeals process | [10 empty] | Only talks of expedited appeals related to provider payment in the provider manual
Field Liaisons
Financial Incentives |  |  |  | X
FWA Prevention/investigation |  |  | 2018-11-23 | Meghan | No
Grievance process policy |  |  | 2018-11-23 | Meghan | No |  |  | 2018-11-23 | Meghan | No
Health Literacy |  |  | 2018-11-26 | Ave | No |  |  | 2018-11-27 | Ave | No
HIPAA Member request compliance |  |  | 2018-11-26 | Ave | yes
Hours of service 365/24/7
Inclement Weather/traffic situations |  |  |  | Meghan
Interaction Handling |  |  | 2018-11-23 | Meghan | No
Levels of service - Curb to curb
Levels of service - Door to door
Management of No shows |  |  |  | Meghan | No |  |  | 2018-11-28 | Meghan | No | just one edit
Marketing Communications |  |  | 2018-11-26 | Ave | No |  |  | 2018-11-27 | Ave | No | need specificity around LEP, alternative formats, prior approval by state process for member communications Health Literacy should be a comp[anion doc to Marketing Communication
Member eligibility |  |  |  | Meghan
Modes of service - Ambulance (ALS/BLS)
Modes of service - Mileage Reimbursement
Modes of service - Multi-Passenger Van
Modes of service - Public Motor Vehicle
Modes of service - Public Transit
Modes of service - Ride Share (Lyft)
Modes of service - Stretcher Van
Modes of service - Volunteer Drivers
Modes of service - Wheelchair Van
Month-end bus reconciliation
MTM Satisfaction survey | [7 empty] | 2018-11-28 | Meghan | yes
Office staff and CCR personnel P&P
Payment process for TPs
Peak transportation contingency plan
Performance improvement plan administration
Performance improvement plan, TP |  |  | 2018-11-26 | Ave | No |  |  |  | Ave | No | needs detail when state is notified and time frames
Post authorization trips | [7 empty] | 2018-12-05 | Meghan | Yes
Power outage system failure |  |  |  | Meghan
Pre and Post Trip Verification P&P
Process for short notice trip requests
Process for TP trip assignment
Provider audit and vehicle inspection
Publication of members' rights |  |  | 2018-11-23 | Meghan | No
Quality & Compliance committee/board |  |  | 2018-11-26 | Ave | No |  |  |  | Ave | No | Title does not reflect content; numbering under Responsibility begins w/#5; where is 1-4,Please review this P&P as it appears there are 2 policies here
Re-credentialing Process |  |  | 2018-11-23 | Meghan | No | [5 empty] | One Edit
Recurring appointments |  |  |  | Meghan
Relaying TP Issues | [7 empty] | 2018-12-05 | Meghan | Yes
Reloadable public transit fare |  |  |  | X
Reporting/handling accidents/incidents
Special Needs transporation scheduling |  |  |  | Meghan
Staff training curriculum (not TPs) including mode of transport determination, cultural |  |  | 2018-11-23 | Meghan | Yes
TP Contracting
TP Credentialing including list of excluded individuals |  |  | 2018-11-23 | Meghan | Yes
TP Help Desk | [7 empty] | 2018-12-05 | Meghan | Yes
TP Incentive program
TP Monitoring, corrective action, termination |  |  | 2018-11-23 | Meghan | No | [5 empty] | One Edit
TP Selection criteria
TP Training including CPR, HIPAA, Cultural, Defensive driver
Translation services |  |  | 2018-11-26 | Ave | No |  |  | 2018-11-27 | Ave | no | need detail re: notifying TPs
Trip Recovery policy
Utilization review policy